JOB SPECIAL PROVISIONS TABLE OF CONTENTS (ROADWAY)

(Job Special Provisions shall prevail over General Special Provisions whenever in conflict therewith.)

A.	General - Federal JSP-09-02L	1

B.	Contract Liquidated Damages JSP- 13-01D	1

C.	Work Zone Traffic Management JSP-02-06N	3

D.	Emergency Provisions and Incident Management JSP-90-11A	5

E.	Project Contact for Contractor/Bidder Questions JSP-96-05A	6

F.	Supplemental Revisions JSP-18-01KK	7

G.	Liquidated Damages for Winter Months JSP-04-17A	14

H.	Liquidated Damages Specified	14

I.	Utilities JSP-93-26F	14

J.	Contractor Quality Control NJSP-15-42	34

K.	No Value Engineering Proposals for 2.5 Inch Perforated Square Steel Tube (PSST) Posts and Concrete Post Anchors for 2.5 Inch Perforated Square Steel Tube (PSST) Posts	36

L.	Damage to Existing Pavement, Shoulders, Side Roads and Entrances	37

M.	Truck Mounted Attenuator (TMA) for Stationary Activities JSP-23-04	37

N.	Optional Pavements JSP 06-06H	38

O.	Pavement Edge Treatment for Drop Off Conditions for Island Removals	39

P.	Lump Sum Temporary Traffic Control JSP-22-01B	39

Q.	ADA Compliance and Final Acceptance of Constructed Facilities JSP-10-01C	41

R.	ADA Material Testing Frequency Modifications JSP-23-01	42

S.	ADA Compliant Moveable Barricade	43

T.	Linear Grading for ADA Facilities - SW	43

U.	Curb Ramps and Sidewalk – SW	44

V.	Accessible Pedestrian Pushbutton Connectivity	45

W.	Signal Controller	46

X.	Signal Detection Disconnection	46

Y.	Contractor Furnished, Contractor Installed Radar Detection System	47

Z.	Flashing Yellow Arrow Implementation Details	49

AA.	Retroreflective Back Plates	50

BB.	Remove and Relocate CCTV Camera	50

CC.	Wireless Connection	51

DD.	Disposition of Existing Signal, Lighting and Network Equipment	51

EE.	Removal and Delivery of Existing Signs JSP-12-01C	52

FF.	Contractor Furnished Surveying and Staking – SW	53

GG.	Seeding and Mulching Requirements JSP-25-03	53

HH.	Removal of License Plate Reader by Others	54

|  | MISSOURI HIGHWAYS AND TRANSPORTATION COMMISSION 105 W. CAPITOL AVE. JEFFERSON CITY, MO 65102 Phone 1-888-275-6636 |
| --- | --- |
|  | GARVER 7509 NW Tiffany Springs Parkway STE 200 Kansas City, MO 64153 Certificate of Authority: 2008013090 Consultant Phone: 816-298-6465 |
|  | If a seal is present on this sheet, JSP’s have been electronically sealed and dated. |
|  | JOB NUMBER: J7P3529 VARIOUS COUNTIES, MO DATE PREPARED: 3/2/2026 |
|  | ADDENDUM DATE: |
| Only the following items of the Job Special Provisions (Roadway) are authenticated by this seal: All |  |

JOB

SPECIAL PROVISION

# General - Federal JSP-09-02L

1.0  Description.  The Federal Government is participating in the cost of construction of this project.  All applicable Federal laws, and the regulations made pursuant to such laws, shall be observed by the contractor, and the work will be subject to the inspection of the appropriate Federal Agency in the same manner as provided in Sec 105.10 of the Missouri Standard Specifications for Highway Construction with all revisions applicable to this bid and contract.

1.1  This contract requires payment of the prevailing hourly rate of wages for each craft or type of work required to execute the contract as determined by the Missouri Department of Labor and Industrial Relations and requires adherence to a schedule of minimum wages as determined by the United States Department of Labor.  For work performed anywhere on this project, the contractor and the contractor’s subcontractors shall pay the higher of these two applicable wage rates. State Wage Rates, Information on the Required Federal Aid Provisions, and the current Federal Wage Rates are available on the Missouri Department of Transportation web page at www.modot.org under "Doing Business with MoDOT”, “Contractor Resources".  Effective Wage Rates will be posted 10 days prior to the applicable bid opening.  These supplemental bidding documents have important legal consequences.  It shall be conclusively presumed that they are in the bidder's possession, and they have been reviewed and used by the bidder in the preparation of any bid submitted on this project.

1.2  The following documents are available on the Missouri Department of Transportation web page at www.modot.org under "Doing Business with MoDOT"; “Standards and Specifications”. The effective version shall be determined by the letting date of the project.

General Provisions & Supplemental Specifications

Supplemental Plans to July 2025 Missouri Standard Plans

For Highway Construction

These supplemental bidding documents contain all current revisions to the published versions and have important legal consequences.  It shall be conclusively presumed that they are in the bidder's possession, and they have been reviewed and used by the bidder in the preparation of any bid submitted on this project.

# Contract Liquidated Damages JSP- 13-01D

1.0  Description.  Liquidated Damages for failure or delay in completing the work on time for this contract shall be in accordance with Sec 108.8.  The liquidated damages include separate amounts for road user costs and contract administrative costs incurred by the Commission.

1.1  Subproject Identification.  Portions of the Contract are hereby identified as subprojects with the following assignment of Bridge Number, Route, or other location of work. This identification is done for the purpose of setting time limits for completion of each subproject and to allow partial acceptance of the work for maintenance as subprojects are completed.

Subproject			Description

A	Location 1 – Route 52 at BL49 – Butler

B	Location 2 – Route 54 at Park St. – El Dorado Springs

C	Location 3 – Route 65 at Route 32 – Buffalo

D	Location 4 – Route 43 at 41st St. - Joplin

E	Location 5 – BL49 at Waldo Hatler Memorial Dr. - Neosho

F	Location 6 – Route 60 at Oak Ridge Dr. - Neosho

G	Location 7 – Route 59 at Route at Route C - Goodman

H	Location 8 – Route 59 at BUS 71 and Route 76 - Anderson

I	Location 9 – BUS 71 at Cedar St. - Anderson

J	Location 10 – BUS 71 at Route W - Pineville

2.0  Period of Performance.  Prosecution of work is expected to begin on the date specified below in accordance with Sec 108.2.  Regardless of when the work is begun on this contract, all work on all projects shall be completed on or before the date specified below.  Completion by this date shall be in accordance with the requirements of Sec 108.7.1.

Notice to Proceed:	July 20, 2026

Contract Completion Date:  December 1, 2027

2.1  Calendar Days.  Completion of the project is required as specified herein. The count of calendar days will begin on the date the contractor starts any construction operations on the project.

Project	Calendar Days	Daily Road User Cost

A	20	$2,300

B	56	$2,300

C	23	$3,200

D	84	$5,400

E	79	$2,300

F	76	$3,200

G	56	$1,800

H	41	$2,300

I	76	$2,300

J	56	$1,800

3.0  Liquidated Damages for Contract Administrative Costs.  Should the contractor fail to complete the work on or before the contract completion date specified in Section 2.0, or within the number of calendar days specified in Section 2.1, whichever occurs first, the contractor will be charged contract administrative liquidated damages in accordance with Sec 108.8 in the amount of $1,500 per calendar day for each calendar day, or partial day thereof, that the work is not fully completed.  For projects in combination, these damages will be charged in full for failure to complete one or more projects within the specified contract completion date or calendar days.

4.0  Liquidated Damages for Road User Costs.  Should the contractor fail to complete the work on or before the contract completion date specified in Section 2.0, or within the number of calendar days specified in Section 2.1, whichever occurs first, the contractor will be charged road user costs in accordance with Sec 108.8 in the amount specified in Section 2.1 for each calendar day, or partial day thereof, that the work is not fully completed.  These damages are in addition to the contract administrative damages and any other damages as specified elsewhere in this contract.

# Work Zone Traffic Management JSP-02-06N

1.0  Description.  Work zone traffic management shall be in accordance with applicable portions of Division 100 and Division 600 of the Standard Specifications, and specifically as follows.

1.1  Maintaining Work Zones and Work Zone Reviews. The Work Zone Specialist (WZS) shall maintain work zones in accordance with Sec 616.3.3 and as further stated herein.  The WZS shall coordinate and implement any changes approved by the engineer.  The WZS shall ensure all traffic control devices are maintained in accordance with Sec 616, the work zone is operated within the hours specified by the engineer, and will not deviate from the specified hours without prior approval of the engineer. The WZS is responsible to manage work zone delay in accordance with these project provisions.  When requested by the engineer, the WZS shall submit a weekly report that includes a review of work zone operations for the week. The report shall identify any problems encountered and corrective actions taken.  Work zones are subject to unannounced inspections by the engineer and other departmental staff to corroborate the validity of the WZS’s review and may require immediate corrective measures and/or additional work zone monitoring.

1.2  Work Zone Deficiencies.  Failure to make corrections on time may result in the engineer suspending work.  The suspension will be non-excusable and non-compensable regardless if road user costs are being charged for closures.

2.0  Traffic Management Schedule.

2.1  Traffic management schedules shall be submitted to the engineer for review prior to the start of work and prior to any revisions to the traffic management schedule.  The traffic management schedule shall include the proposed traffic control measures, the hours traffic control will be in place, and work hours.

2.2  The traffic management schedule shall conform to the limitations specified in Sec 616 regarding lane closures, traffic shifts, road closures and other width, height and weight restrictions.

2.3  The engineer shall be notified as soon as practical of any postponement due to weather, material or other circumstances.

2.4  In order to ensure minimal traffic interference, the contractor shall schedule lane closures for the absolute minimum amount of time required to complete the work.  Lanes shall not be closed until material is available for continuous construction and the contractor is prepared to diligently pursue the work until the closed lane is opened to traffic.

2.5  Traffic Congestion.  The contractor shall, upon approval of the engineer, take proactive measures to reduce traffic congestion in the work zone.  The contractor shall immediately implement appropriate mitigation strategies whenever traffic congestion reaches an excess of 10 minutes to prevent congestion from escalating to 15 minute or above threshold.  If disruption of the traffic flow occurs and traffic is backed up in queues of 15 minute delays or longer, then the contractor shall immediately review the construction operations which contributed directly to disruption of the traffic flow and make adjustments to the operations to prevent the queues from reoccurring.  Traffic delays may be monitored by physical presence on site or by utilizing real-time travel data through the work zone that generate text and/or email notifications where available.  The engineer monitoring the work zone may also notify the contractor of delays that require prompt mitigation.  The contractor may work with the engineer to determine what other alternative solutions or time periods would be acceptable.

2.5.1	Traffic Safety.

2.5.1.1 Recurring Congestion.  Where traffic queues routinely extend to within 1000 feet of the ROAD WORK AHEAD, or similar, sign on a divided highway or to within 500 feet of the ROAD WORK AHEAD, or similar, sign on an undivided highway, the contractor shall extend the advance warning area, as approved by the engineer.

2.5.1.2 Non-Recurring Congestion.  When traffic queues extend to within 1000 feet of the ROAD WORK AHEAD, or similar, sign on a divided highway or to within 500 feet of the ROAD WORK AHEAD, or similar, sign on an undivided highway infrequently, the contractor shall deploy a means of providing advance warning of the traffic congestion, as approved by the engineer. The warning location shall be no less than 1000 feet and no more than 0.5 mile in advance of the end of the traffic queue on divided highways and no less than 500 feet and no more than 0.5 mile in advance of the end of the traffic queue on undivided highways.

3.0  Work Hour Restrictions.

3.1  Except for emergency work, as determined by the engineer, and long term lane closures required by project phasing, all lanes shall be scheduled to be open to traffic during the five major holiday periods shown below, from 12:00 noon on the last working day preceding the holiday until 6:00 a.m. on the first working day subsequent to the holiday unless otherwise approved by the engineer.

Memorial Day

Labor Day

Thanksgiving

Christmas

New Year’s Day

3.1.1 Independence Day.  The lane restrictions specified in Section 3.1 shall also apply to Independence Day, except that the restricted periods shall be as follows:

| When Independence Day falls on: | The Holiday is Observed on: | Halt Lane Closures beginning at: | Allow Lane Closures to resume at: |
| --- | --- | --- | --- |
| Sunday | Monday | Noon on Friday | 6:00 a.m. on Tuesday |
| Monday | Monday | Noon on Friday | 6:00 a.m. on Tuesday |
| Tuesday | Tuesday | Noon on Monday | 6:00 a.m. on Wednesday |
| Wednesday | Wednesday | Noon on Tuesday | 6:00 a.m. on Thursday |
| Thursday | Thursday | Noon on Wednesday | 6:00 a.m. on Friday |
| Friday | Friday | Noon on Thursday | 6:00 a.m. on Monday |
| Saturday | Friday | Noon on Thursday | 6:00 a.m. on Monday |

3.2  The contractor shall not perform any construction operation on the roadway, including the hauling of material within the project limits, during restricted periods, holiday periods or other special events specified in the contract documents.

3.3  Any work requiring a reduction in the number of through lanes of traffic at Location 4 – Route 43 at 41st St. in Joplin shall be completed during nighttime hours.  Nighttime hours shall be considered to be 7:00 p.m. to 6:00 a.m. for this project.

4.0  Detours and Lane Closures.

4.1  When a changeable message sign (CMS) is provided, the contractor shall use the CMS to notify motorists of future traffic disruption and possible traffic delays one week before traffic is shifted to a detour or prior to lane closures.  The CMS shall be installed at a location as approved or directed by the engineer.  If a CMS with Communication Interface is required, then the  CMS shall be capable of communication prior to installation on right of way.  All messages planned for use in the work zone shall be approved and authorized by the engineer or its designee prior to deployment.  When permanent dynamic message signs (DMS) owned and operated by MoDOT are located near the project, they may also be used to provide warning and information for the work zone.  Permanent DMS shall be operated by the TMC, and any messages planned for use on DMS shall be approved and authorized by the TMC at least 72 hours in advance of the work.

5.0  Basis of Payment.  No direct payment will be made to the contractor to recover the cost of equipment, labor, materials, or time required to fulfill the above provisions, unless specified elsewhere in the contract document.  All authorized changes in the traffic control plan shall be provided for as specified in Sec 616.

# Emergency Provisions and Incident Management JSP-90-11A

1.0  The contractor shall have communication equipment on the construction site or immediate access to other communication systems to request assistance from law enforcement or other emergency agencies for incident management.  In case of traffic accidents or the need for law enforcement to direct or restore traffic flow through the job site, the contractor shall notify law enforcement or other emergency agencies immediately as needed.  The area engineer's office shall also be notified when the contractor requests emergency assistance.

2.0  In addition to the 911 emergency telephone number for ambulance, fire or law enforcement services, the following agencies may also be notified for accident or emergency situation within the project limits.

| Missouri Highway Patrol - Troop A: 816-622-0800 |  |
| --- | --- |
| MoDOT Customer Service: 417-895-7600 |  |
| Bates County Sheriff | 660-679-3232 |
| Butler Police | 660-679-6131 |
| Butler Fire | 660-679-6323 |

| Missouri Highway Patrol - Troop D: 417-895-6868 |  |
| --- | --- |
| MoDOT Customer Service: 417-895-7600 |  |
| Cedar County Sheriff | 417-276-5133 |
| El Dorado Springs Police | 417-876-2313 |
| El Dorado Springs Fire | 417-876-4099 |
| Dallas County Sheriff | 417-345-2441 |
| Buffalo Police | 417-345-2709 |
| Buffalo Fire | 417-345-7800 |
| Newton County Sheriff | 417-451-8300 |
| Joplin Police | 417-623-3131 |
| Joplin Fire | 417-624-0820 |
| Neosho Police | 417-451-8012 |
| Neosho Fire | 417-451-8300 |
| McDonald County Sheriff | 417-223-4319 |
| Goodman Police | 417-223-4318 |
| Goodman Fire | 417-364-8631 |
| Anderson Police | 417-845-3723 |
| Anderson Fire | 417-845-6202 |
| Pineville Police | 417-223-4369 |
| Pineville Fire | 417-223-4368 |

Emergency Only Numbers

911

*55 cell phone – Missouri State Highway Patrol

417-864-1160 cell – MoDOT Incident Management Coordinator

2.1  This list is not all inclusive.  Notification of the need for wrecker or tow truck services will remain the responsibility of the appropriate law enforcement agency.

2.2  The contractor shall notify law enforcement and emergency agencies before the start of construction to request their cooperation and to provide coordination of services when emergencies arise during the construction at the project site.  When the contractor completes this notification with law enforcement and emergency agencies, a report shall be furnished to the engineer on the status of incident management.

3.0  No direct pay will be made to the contractor to recover the cost of the communication equipment, labor, materials or time required to fulfill the above provisions.

# Project Contact for Contractor/Bidder Questions JSP-96-05A

1.0  All questions concerning this project during the bidding process shall be forwarded to the project contact listed below.

Shannon Kellner, Project Contact

Southwest District

1057 E. Gaines Drive

Clinton, MO 64735

Telephone Number: (417) 880-8046

Email:  Shannon.Kellner@modot.mo.gov

1.1  All questions concerning the bid document preparation can be directed to the Central Office – Design as listed below.

Telephone Number: (573) 751-2876

Email:  BCS@modot.mo.gov

# Supplemental Revisions JSP-18-01KK

- Compliance with 2 CFR 200.216 – Prohibition on Certain Telecommunications and Video Surveillance Services or Equipment.

The Missouri Highways and Transportation Commission shall not enter into a contract (or extend or renew a contract) using federal funds to procure or obtain equipment, services, or systems that uses covered telecommunications equipment or services as substantial or as critical technology as part of any system where the video surveillance and telecommunications equipment was produced by Huawei Technologies Company, ZTE Corporation, Hytera Communications Corporation, Hangzhou Hikvision Digital Technology Company, or Dahua Technology Company (or any subsidiary or affiliate of such entities).

- Stormwater Compliance Requirements

1.0  Description.  This provision requires the contractor to provide a Water Pollution Control Manager (WPCM) for any project that includes land disturbance on the project site and the total area of land disturbance, both on the project site, and all Off-site support areas, is one (1) acre or more.  Regardless of the area of Off-site disturbance, if no land disturbance occurs on the project site, these provisions do not apply.  When a WPCM is required, all sections within this provision shall be applicable, including assessment of specified Liquidated Damages for failure to correct Stormwater Deficiencies, as specified herein.  This provision is in addition to any other stormwater, environmental, and land disturbance requirements specified elsewhere in the contract.

1.1  Definitions.  The project site is defined as all areas designated on the plans, including temporary and permanent easements.  The project site is equivalent to the “permitted site”, as defined in MoDOT’s State Operating Permit.  An Off-site area is defined as any location off the project site the contractor utilizes for a dedicated project support function, such as, but not limited to, staging area, plant site, borrow area, or waste area.

1.2  Reporting of Off-Site Land Disturbance.  If the project includes any planned land disturbance on the project site, prior to the start of work, the contractor shall submit a written report to the engineer that discloses all Off-site support areas where land disturbance is planned, the total acreage of anticipated land disturbance on those sites, and the land disturbance permit number(s).  Upon request by the engineer, the contractor shall submit a copy of its land disturbance permit(s) for Off-site locations.  Based on the total acreage of land disturbance, both on and Off-site, the engineer shall determine if these Stormwater Compliance Requirements shall apply.  The Contractor shall immediately report any changes to the planned area of Off-site land disturbance.  The Contractor is responsible for obtaining its own separate land disturbance permit for Off-site areas.

2.0  Water Pollution Control Manager (WPCM).  The Contractor shall designate a competent person to serve as the Water Pollution Control Manager (WPCM) for projects meeting the description in Section 1.0.  The Contractor shall ensure the WPCM completes all duties listed in Section 2.1.

2.1  Duties of the WPCM:

- Be familiar with the stormwater requirements including the current MoDOT State Operating Permit for construction stormwater discharges/land disturbance activities; MoDOT’s statewide Stormwater Pollution Prevention Plan (SWPPP); the Corps of Engineers Section 404 Permit, when applicable; the project specific SWPPP, the Project’s Erosion & Sediment Control Plan; all applicable special provisions, specifications, and standard drawings; and this provision;

- Successfully complete the MoDOT Stormwater Training Course within the last 4 years.  The MoDOT Stormwater Training is a free online course available at MoDOT.org;

- Attend the Pre-Activity Meeting for Grading and Land Disturbance and all subsequent Weekly Meetings in which grading activities are discussed;

- Oversee and ensure all work is performed in accordance with the Project-specific SWPPP and all updates thereto, or as designated by the engineer;

- Review the project site for compliance with the Project SWPPP, as needed, from the start of any grading operations until final stabilization is achieved, and take necessary actions to correct any known deficiencies to prevent pollution of the waters of the state or adjacent property owners prior to the engineer’s weekly inspections;

- Review and acknowledge receipt of each MoDOT Inspection Report (Land Disturbance Inspection Record) for the Project within forty eight (48) hours of receiving the report and ensure that all Stormwater Deficiencies noted on the report are corrected as soon as possible, but no later than stated in Section 5.0.

3.0  Pre-Activity Meeting for Grading/Land Disturbance and Required Hold Point.  A Pre-Activity meeting for grading/land disturbance shall be held prior to the start of any land disturbance operations.  No land disturbance operations shall commence prior to the Pre-Activity meeting except work necessary to install perimeter controls and entrances.  Discussion items at the pre-activity meeting shall include a review of the Project SWPPP, the planned order of grading operations, proposed areas of initial disturbance, identification of all necessary BMPs that shall be installed prior to commencement of grading operations, and any issues relating to compliance with the Stormwater requirements that could arise in the course of construction activity at the project.

3.1  Hold Point.  Following the pre-activity meeting for grading/land disturbance and subsequent installation of the initial BMPs identified at the pre-activity meeting, a Hold Point shall occur prior to the start of any land disturbance operations to allow the engineer and WPCM the time needed to perform an on-site review of the installation of the BMPs to ensure compliance with the SWPPP is met.  Land disturbance operations shall not begin until authorization is given by the engineer.

4.0  Inspection Reports.  Weekly and post run-off inspections will be performed by the engineer and each Inspection Report (Land Disturbance Inspection Record) will be entered into a web-based Stormwater Compliance database.  The WPCM will be granted access to this database and shall promptly review all reports, including any noted deficiencies, and shall acknowledge receipt of the report as required in Section 2.1 (f.).

5.0  Stormwater Deficiency Corrections.  All stormwater deficiencies identified in the Inspection Report shall be corrected by the contractor within 7 days of the inspection date or any extended period granted by the engineer when weather or field conditions prohibit the corrective work.  If the contractor does not initiate corrective measures within 5 calendar days of the inspection date or any extended period granted by the engineer, all work shall cease on the project except for work to correct these deficiencies, unless otherwise allowed by the engineer.  All impact costs related to this halting of work, including, but not limited to stand-by time for equipment, shall be borne by the Contractor.  Work shall not resume until the engineer approves the corrective work.

5.1  Liquidated Damages.  If the Contractor fails to complete the correction of all Stormwater Deficiencies listed on the MoDOT Inspection Report within the specified time limit, the Commission will be damaged in various ways, including but not limited to, potential liability, required mitigation, environmental clean-up, fines, and penalties.  These damages are not reasonably capable of being computed or quantified.  Therefore, the contractor will be charged with liquidated damages specified in the amount of $2,000 per day for failure to correct one or more of the Stormwater Deficiencies listed on the Inspection Report within the specified time limit.  In addition to the stipulated damages, the stoppage of work shall remain in effect until all corrections are complete.

6.0  Basis of Payment.  No direct payment will be made for compliance with this provision.

- Delete Sec 106.9 in its entirety and substitute the following:

106.9  Buy America Requirements.

Buy America Requirements are waived if the total amount of Federal financial assistance applied to the project, through awards or subawards, is below $500,000.

106.9.1  Buy America Requirements for Iron or Steel Products.

The contractor’s attention is directed to Title 23 CFR 635.410 Buy America Requirements.  Where articles, materials or supplies that consist wholly or predominantly of iron or steel or a combination of both are to be permanently incorporated into the contract work, steel and iron material shall be manufactured, from the initial melting stage through the application of coatings, in the USA except for “minimal use” as described herein.  Predominantly of iron or steel or a combination of both means that the cost of the iron and steel content exceeds 50 percent of the total cost of all its components.  Under a general waiver from FHWA the use of pig iron and processed, pelletized, and reduced iron ore manufactured outside of the USA will be permitted in the domestic manufacturing process for steel or iron material.

106.9.1.1  Any sources other than the USA as defined will be considered foreign.  The required domestic manufacturing process shall include formation of ingots and any subsequent process.  Coatings shall include any surface finish that protects or adds value to the product.

106.9.1.2  “Minimal use” of foreign steel, iron or coating processes will be permitted, provided the cost of such products does not exceed 1/10 of one percent (0.1 percent) of the total contract cost or $2,500.00, whichever is greater.  If foreign steel, iron, or coating processes are used, invoices to document the cost of the foreign portion, as delivered to the project, shall be provided and the engineer’s written approval obtained prior to placing the material in any work.

106.9.1.3  Buy America requirements include a step certification for all fabrication processes of all steel or iron materials that are accepted per Sec 1000.  The AASHTO Product Evaluation and Audit Solutions compliance program verifies that all steel and iron products fabrication processes conform to 23 CFR 635.410 Buy America Requirements and is an acceptable standard per 23 CFR 635.410(d).  AASHTO Product Evaluation and Audit Solutions compliant suppliers will not be required to submit step certification documentation with the shipment for some selected steel and iron materials.  The AASHTO Product Evaluation and Audit Solutions compliant supplier shall maintain the step certification documentation on file and shall provide this documentation to the engineer upon request.

106.9.1.3.1  Items designated as Category 1 will consist of steel girders, piling, and reinforcing steel installed on site.  Category 1 items require supporting documentation prior to incorporation into the project showing all steps of manufacturing, including coating, as being completed in the United States and in accordance with CFR Title 23 Section 635.410 Buy America Requirements.  This includes the Mill Test Report from the original producing steel mill and certifications documenting the manufacturing process for all subsequent fabrication, including coatings. The certification shall include language that certifies all steel and iron materials permanently incorporated in this project was procured and processed domestically and all manufacturing processes, including coating, as being completed in the United States and in accordance with CFR Title 23 Section 635.410.

106.9.1.3.2  Items designated as Category 2 will include all other steel or iron products not in Category 1 and permanently incorporated in the project.  Category 2 items shall consist of, but not be limited to items such as fencing, guardrail, signing, lighting and signal supports.  The prime contractor is required to submit a material of origin form certification prior to incorporation into the project from the fabricator for each item that the product is domestic.  The Certificate of Materials Origin form (link to certificate form) from the fabricator must show all steps of manufacturing, including coating, as being completed in the United States and in accordance with CFR Title 23 Section 635.410 Buy America Requirements and be signed by a fabricator representative.  The engineer reserves the right to request additional information and documentation to verify that all Buy America requirements have been satisfied.  These documents shall be submitted upon request by the engineer and retained for a period of 3 years after the last reimbursement of the material.

106.9.1.3.3  Any minor miscellaneous steel or iron items that are not included in the materials specifications shall be certified by the prime contractor as being procured domestically.  Examples of these items would be bolts for sign posts, anchorage inserts, etc.  The certification shall read “I certify that all steel and iron materials permanently incorporated in this project during all manufacturing processes, including coating, as being completed in the United States and in accordance with CFR Title 23 Section 635.410 Buy America Requirements procured and processed domestically in accordance with CFR Title 23 Section 635.410 Buy America Requirements.  Any foreign steel used was submitted and accepted under minor usage”.  The certification shall be signed by an authorized representative of the prime contractor.

106.9.1.4  When permitted in the contract, alternate bids may be submitted for foreign steel and iron products.  The award of the contract when alternate bids are permitted will be based on the lowest total bid of the contract based on furnishing domestic steel or iron products or 125 percent of the lowest total bid based on furnishing foreign steel or iron products.  If foreign steel or iron products are awarded in the contract, domestic steel or iron products may be used; however, payment will be at the contract unit price for foreign steel or iron products.

106.9.2  Buy America Requirements for Construction Materials other than iron or steel products.

Construction materials mean articles, materials, or supplies that consist of only one of the items listed.  Minor additions of articles, materials, supplies, or binding agents to a construction material do not change the categorization of the construction material.  Upon request by the engineer, the contractor shall submit a domestic certification for all construction materials listed that are incorporated into the project.

- Non-ferrous metals

- Plastic and Polymer-based products (including polyvinylchloride, composite building materials, and polymers used in fiber optic cables)

- Glass (including optic glass)

- Fiber optic cable (including drop cable)

- Optical fiber

- Lumber

- Engineered wood

- Drywall

106.9.3  Buy America Requirements for Manufactured Products.

Manufactured products mean articles, materials or supplies that have been processed into a specific form and shape, or combined with other articles, materials or supplies to create a product with different properties than the individual articles, materials or supplies. If an item is classified as an iron or steel product, an excluded material, or other product category as specified by law or in 2 CFR part 184, then it is not a manufactured product. However, an article, material or supply classified as a manufactured product may include components that are iron or steel products, excluded materials, or other product categories as specified by law or in 2 CFR part 184. Mixtures of excluded materials delivered to a work site without final form for incorporation into a project are not a manufactured product.

106.9.3.1  Produced in the United States, in the case of manufactured products, means:

(A) For projects obligated on or after October 1, 2025, the product was manufactured in the United States; and

(B) For projects obligated on or after October 1, 2026, the product was manufactured in the United States and the cost of the components of the manufactured product that are mined, produced, or manufactured in the United States is greater than 55 percent of the total cost of all components of the manufactured product.

106.9.3.2  (i) With respect to precast concrete products that are classified as manufactured products, components of precast concrete products that consist wholly or predominantly of iron or steel or a combination of both shall meet the requirements of paragraph (b) of this section. The cost of such components shall be included in the applicable calculation for purposes of determining whether the precast concrete product is produced in the United States.

(ii) With respect to intelligent transportation systems and other electronic hardware systems that are installed in the highway right of way or other real property and classified as manufactured products, the cabinets or other enclosures of such systems that consist wholly or predominantly of iron or steel or a combination of both shall meet the requirements of paragraph (b) of this section. The cost of cabinets or other enclosures shall be included in the applicable calculation for purposes of determining whether systems referred to in the preceding sentence are produced in the United States.

106.9.4  Waiver for De Minimis Costs for Manufactured and Construction Materials other than iron or steel products.

“The total value of the non-compliant products is no more than the lesser of $1,000,000 or 5% of total applicable costs for the project.”  The contractor shall submit to the engineer any non-domestic materials and their total material cost to the engineer.  The contractor and the engineer will both track these totals to assure that the minimal usage allowance is not exceeded.

- Third-Party Test Waiver for Concrete Aggregate

1.0  Description.  Third party tests may be allowed for determining the durability factor for concrete pavement and concrete masonry aggregate.

2.0  Material.  All aggregate for concrete shall be in accordance with Sec 1005.

2.1  MoDOT personnel shall be present at the time of sampling at the quarry.  The aggregate sample shall be placed in an approved tamper-evident container (provided by the quarry) for shipment to the third-party testing facility.

2.2  AASHTO T 161 Method B Resistance of Concrete to Rapid Freezing and Thawing, shall be used to determine the aggregate durability factor.  All concrete beams for testing shall be 3-inch wide by 4-inch deep by 16-inch long or 3.5-inch wide by 4.5-inch deep by 16-inch long.  All beams for testing shall receive a 35-day wet cure fully immersed in saturated lime water prior to initiating the testing process.

2.3  Concrete test beams shall be made using a MoDOT approved concrete pavement mix design.

3.0  Testing Facility Requirements.  All third-party test facilities shall meet the requirements outlined in this provision.

3.1  The testing facility shall be AASHTO accredited.

3.1.1  For tests ran after January 1, 2025, accreditation documentation shall be on file with the Construction and Materials Division prior to any tests being performed.

3.1.2  Construction and Materials Division may consider tests completed prior to January 1, 2025, to be acceptable if all sections of this provision are met, with the exception of 3.1.1.  Accreditation documentation shall be provided with the test results for tests completed prior to January 1, 2025.  No tests completed prior to September 1, 2024, will be accepted.

3.2  The testing facility shall provide their testing process, list of equipment, equipment calibration documentation, and testing certifications or qualifications of technicians performing the AASHTO T 161 Procedure B tests.  The testing facility shall provide details on their freezing and thawing apparatus including the time and temperature profile of their freeze-thaw chamber.  The profile shall include the temperature set points throughout the entirety of the freeze-thaw cycle.  The profile shall show the cycle time at which the apparatus drains/fills with water and the cycle time at which the apparatus begins cooling the specimens.

3.3  Results, no more than five years old, from the third-party test facility shall compare within ±2.0 percent of an independent test from another AASHTO accredited test facility or with MoDOT test records, in order to be approved for use (e.g. test facility results in a durability factor of 79, MoDOT’s recent durability test factor is 81; this compared within +2 percent).  The independent testing facility shall be in accordance with this provision.  The comparison test can be from a different sample of the same ledge combination.

3.4  When there is a dispute between the third party durability test results and MoDOT durability test results, the MoDOT durability test result shall govern.

3.5  Test results shall be submitted to MoDOT’s Construction and Materials division electronically for final approval.  Test results shall include raw data for all measurements of relative dynamic modulus of elasticity and percent length change for each individual concrete specimen.  Raw data shall include initial measurements made at zero cycles and every subsequent measurement of concrete specimens.  Raw data shall include the cycle count and date each measurement was taken.  Test results shall also include properties of the concrete mixture as required by AASHTO T 161.  This shall include the gradation of the coarse aggregate sample.  If AASHTO T 152 is used to measure fresh air content, then the aggregate correction factor for the mix determined in accordance with AASHTO T 152 shall also be included.

4.0  Method of Measurement.  There is no method of measurement for this provision.  The testing requirements and number of specimens shall be in accordance with AASHTO T 161 Procedure B.

5.0  Basis of Payment.  No direct payment will be made to the contractor or quarry to recover the cost of aggregate samples, sample shipments, testing equipment, labor to prepare samples or test samples, or developing the durability report.

- Delete paragraph 15.0 of the General Provision Disadvantaged Business Enterprise (DBE) Program Requirements and substitute the following:

15.0  Bidder’s List Quote Summary.  MoDOT is a recipient of federal funds and is required by 49 CFR 26.11 to provide data about its DBE program.  All bidders who seek to work on federally assisted contracts must submit data about all DBE and non-DBEs in accordance with Sec 102.7.9.  MoDOT will not compare the submitted Bidder’s List Quote Summary to any other documents or submittals, pre or post award.  All information will be used by MoDOT in accordance with 49 CFR 26.11 for reporting to USDOT and to aid in overall DBE goal setting.

- Add Sec 102.7.9 to include the following:

102.7.9 Bidder’s List Quote Summary.  Each bidder shall submit with each bid a summary of all subcontractors, material suppliers, and service providers (e.g. hauling) considered on federally funded projects pursuant to 49 CFR 26.11.  The bidder will provide the firm’s name, the corresponding North American Industry Classification System (NAICS) code(s) the firm(s) were considered for, and whether or not they were used in the bid.  The information submitted should be the most complete information available at the time of bid.  The information shall be disclosed on the Bidder’s List Quote Summary form provided in the bidding documents and submitted in accordance with Sec 102.10.  Failure to disclose this information may result in a bid being declared irregular.

# Liquidated Damages for Winter Months JSP-04-17A

Delete Sec 108.8.1.3 (a)

Liquidated damages for failure to complete the work on time shall not be waived from December 15 to March 15, both dates inclusive.

# Liquidated Damages Specified

1.0  Description.  If any lanes of Route 43 (Main St.) in Joplin are not open to traffic by 6:00 a.m. each day following a nighttime lane closure, the Commission, the traveling public, and state and local police and governmental authorities will be damaged in various ways, including but not limited to, increased construction administration cost, potential liability, traffic and traffic flow regulation cost, traffic congestion and motorist delay, with its resulting cost to the traveling public.  These damages are not reasonably capable of being computed or quantified.  Therefore, the contractor will be charged with liquidated damages specified according to the following schedule.

- If any lane or lanes of Route 43 (Main St.) are closed for any time between 6:00 a.m. to 7:00 a.m., the contractor shall be charged in the amount of $500 for that hour or any fraction of that hour.

- If any lane or lanes of Route 43 (Main St.) are closed for any time between 7:00 a.m. to 8:00 a.m., the contractor shall be charged in the amount of $1,000 for that hour or any fraction of that hour.

- If any lane or lanes of Route 43 (Main St.) are closed for any time between 8:00 a.m. to 9:00 a.m., the contractor shall be charged in the amount of $1,200 for that hour or any fraction of that hour.

- If any lane or lanes of Route 43 (Main St.) are closed for any time between 9:00 a.m. to 10:00 a.m., the contractor shall be charged in the amount of $1,400 for that hour or any fraction of that hour.

- If any lane or lanes of Route 43 (Main St.) are closed for any time after 10:00 a.m., the contractor shall be charged in the amount of $900 for the remaining day not to exceed $5,000 for each full day or fraction of a day that all lanes are not open to traffic.

1.1  All liquidated damages specified are in excess of the limitation as specified elsewhere in this special provision.  It shall be the responsibility of the engineer to determine the quantity of excess closure time.

1.2   The said liquidated damages specified will be assessed regardless of whether it would otherwise be charged as liquidated damages under the Missouri Standard Specification for Highway Construction, as amended elsewhere in this contract.

# Utilities JSP-93-26F

1.0  For informational purposes only, the following is a list of names, addresses, and telephone  numbers of the known utility companies in the area of the construction work for this improvement:

Location 1 – LP49 at MO52 in Butler (Bates County)

Known Required

Utility Name	Adjustment	Type

Brightspeed	No	Communications

Nick Brunner

210 E. Market St.

Warrensburg, MO  64093

Phone:  660-441-2435

Email:  nick.a.brunner@brightspeed.com

City of Butler - Electric	No	Power

Travis Gillis

206 E. Mill St.

Butler, MO  64730

Phone:  660-679-5502

Email:  electricdepartment@cityofbutlermo.com

City of Butler - Sewer & Water	No	Sanitary Sewer & Water

Branden Berry

206 E. Mill St.

Butler, MO  64730

Phone:  660-679-3061

Email:  waterdepartment@cityofbutlermo.com

Liberty Utilities	No	Gas

Josh Francis

819 E. Minnesota Ave.

Nevada, MO  64772

Phone:  417-768-9615

Email:  josh.francis@libertyutilities.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

Mediacom	No	Communications

Scott Hunker

1211 Wilkes Blvd.

Columbia, MO  65201

Phone:  573-489-6839

Email:  shunker@mediacomcc.com

Osage Valley Electric Coop. - Fiber	No	Communications

Trevon Riley

1321 N. Orange St.

Butler, MO  64730

Phone:  660-679-3131

Email:  triley@osagevalley.com

Justin Wenger w/Conexon

Phone:  816-266-7631

Email:  justin.wenger@conexon.us

Location 2 – US54 at Park St. in El Dorado Springs (Cedar County)

Known Required

Utility Name	Adjustment	Type

Brightspeed	Yes	Communications

Mike Edwards	(see section 2.1)

2601 Waukesha Road

Siloam Springs, AR  72761

Phone:  479-238-4778

Email:  michael.edwards@brightspeed.com

City of Eldorado Springs	Yes	Power, Sanitary

Joe Robison	(see sections 2.2 & 2.2.1)	Sewer, & Water

135 W. Spring St.

El Dorado Springs, MO  64744

Phone:  417-876-4821

Email:  utilities@eldomo.org

Fidelity Communications	Yes	Communications

Nathan Kitchen	(see section 2.3)

501 N. Washington St.

Salem, MO  65560

Phone:  573-368-6446

Email:  nathan.kitchen@fidelitycommunications.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

Sho-Me Technologies	Yes	Communications

Jim Salaki	(see section 2.4)

P.O. Box D

Marshfield, MO  65706

Phone:  417-701-3793

Email:  jsalaki@shomepower.com

Spire Energy	No	Gas

Baylee Godat	(see section 2.5)

3025 SE Clover Dr.

Lee’s Summit, MO  64082

Phone:  816-334-8075

Email:  baylee.godat@spireenergy.com

Location 3 – US65 at MO32 in Buffalo (Dallas County)

Known Required

Utility Name	Adjustment	Type

Brightspeed	No	Communications

Kelly Weigle

117 N. Madison Ave.

Lebanon, MO  65536

Phone:  417-733-7866

Email:  kelly.weigle1@brightspeed.com

City of Buffalo	No	Sanitary Sewer & Water

Jennifer Killion

115 S. Maple St.

Buffalo, MO  65622

Phone:  417-345-2701

Email:  billingclerk@cityofbuffalomo.gov

Fidelity Communications	No	Communications

Nathan Kitchen

501 N. Washington St.

Salem, MO  65560

Phone:  573-368-6446

Email:  nathan.kitchen@fidelitycommunications.com

Liberty Utilities	No	Power

Allec Uber

3400 S. Kodiak Road

Joplin, MO  64804

Phone:  417-291-0170

Email:  allec.uber@libertyutilities.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Joe Dotson	(see section 1.2)

2455 N. Mayfair Ave.

Springfield, MO  65803

Phone:  417-733-0664

Email:  joseph.dotson@modot.mo.gov

Sho-Me Technologies	No	Communications

Jim Salaki

P.O. Box D

Marshfield, MO  65706

Phone:  417-701-3793

Email:  jsalaki@shomepower.com

Location 4 – MO43 at 41st Street in Joplin (Newton County)

Known Required

Utility Name	Adjustment	Type

Allo Fiber	No	Communications

Chris Rowley

512 S. Main St.

Joplin, MO  64801

Phone:  402-430-2870

Email:  chris.rowley@allofiber.com

AT&T – Distribution	No	Communications

Gene Lollis

727 S. Pearl Ave.

Joplin, MO  64801

Phone:  417-499-7819

Email:  il0967@att.com

City of Joplin	No	Sanitary Sewer

John Cruz

602 S. Main Street

Joplin, MO  64801

Phone:  417-624-0820 ext. 1584

Email:  jcruz@joplinmo.org

Liberty Utilities	Yes	Power

Allec Uber	(see sections 4.1 & 4.1.1)

3400 S. Kodiak Road

Joplin, MO  64804

Phone:  417-291-0170

Email:  allec.uber@libertyutilities.com

Local Contact: McGwire Rice

Phone:  417-560-7702

Email:  mcgwire.rice@libertyutilities.com

Liberty Connect	No	Communications

Landon Dobbs

720 Schifferdecker Ave.

Joplin, MO  64802

Phone:  417-483-2460

Email:  landon.dobbs@libertyutilities.com

Missouri American	No	Water

Matt Hanna

2323 Davis Blvd.

Joplin, MO  64801

Phone:  417-529-9783

Email:  matthew.hanna@amwater.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

Spire Energy	No	Gas

Baylee Godat	(see section 4.2)

3025 SE Clover Dr.

Lee’s Summit, MO  64082

Phone:  816-334-8075

Email:  baylee.godat@spireenergy.com

Sparklight (Cable One)	No	Communications

Keri Bledsoe

2600 S. Davis Blvd.

Joplin, MO  64804

Phone:  417-768-9183

Email:  keri.bledsoe@sparklight.biz

Location 5 – LP49 at Waldo Hatler Dr. in Neosho (Newton County)

Known Required

Utility Name	Adjustment	Type

AT&T – Distribution	No	Communications

Gene Lollis	(see section 5.1)

727 S. Pearl Ave.

Joplin, MO  64801

Phone:  417-499-7819

Email:  il0967@att.com

City of Neosho	No	Sanitary Sewer & Water

Jeff Barratt

200 Nelson Ave.

Neosho, MO  64850

Phone:  417-451-8071

Email:  jbarratt@neoshomo.org

Liberty Utilities	Yes	Power

Allec Uber	(see sections 4.1.1 & 5.2)

3400 S. Kodiak Road

Joplin, MO  64804

Phone:  417-291-0170

Email:  allec.uber@libertyutilities.com

Local Contact: Bill Corlett

Phone:  417-540-9037

Email:  bill.corlett@libertyutilities.com

Lumen	No	Communications

Kimberly Singleton, Engineering Manager	(see section 5.3)

Phone:  419-631-4683

Email:  kimberly.singleton@lumen.com

Olsson (Lumen’s contract engineer)

Sandra Munoz-Cabuya

7301 W. 133rd Street, Suite 200

Overland Park, KS  66213

Phone:  913-748-2646

Email:  smunozcabuya@olsson.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

Ozark Fiber	No	Communications

Jesse Moore

3919 Hollow View Ct.

Wildwood, MO  63069

Phone:  417-242-8341

Email:  jesse.moore@ozarkfiber.com

Spire Energy	No	Gas

Baylee Godat

3025 SE Clover Dr.

Lee’s Summit, MO  64082

Phone:  816-334-8075

Email:  baylee.godat@spireenergy.com

Location 6 – US60 at Oak Ridge Dr. in Neosho (Newton County)

Known Required

Utility Name	Adjustment	Type

AT&T – Distribution	No	Communications

Gene Lollis

727 S. Pearl Ave.

Joplin, MO  64801

Phone:  417-499-7819

Email:  il0967@att.com

City of Neosho	No	Sanitary Sewer & Water

Jeff Barratt

200 Nelson Ave.

Neosho, MO  64850

Phone:  417-451-8071

Email:  jbarratt@neoshomo.org

Liberty Utilities	Yes	Power

Allec Uber	(see sections 4.1.1, 6.1 & 6.2)

3400 S. Kodiak Road

Joplin, MO  64804

Phone:  417-291-0170

Email:  allec.uber@libertyutilities.com

Local Contact: Bill Corlett

Phone:  417-540-9037

Email:  bill.corlett@libertyutilities.com

Liberty Connect	No	Communications

Landon Dobbs

720 Schifferdecker Ave.

Joplin, MO  64802

Phone:  417-483-2460

Email:  landon.dobbs@libertyutilities.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

Optimum	No	Communications

Tony Gilbert

304 S. Madison Ave.

Aurora, MO  65605

Phone:  417-298-4256

Email:  tony.gilbert2@optimum.com

Ozark Fiber	No	Communications

Jesse Moore

3919 Hollow View Ct.

Wildwood, MO  63069

Phone:  417-242-8341

Email:  jesse.moore@ozarkfiber.com

Spire Energy	No	Gas

Baylee Godat

3025 SE Clover Dr.

Lee’s Summit, MO  64082

Phone:  816-334-8075

Email:  baylee.godat@spireenergy.com

Location 7 – MO59 at Route C in Goodman (McDonald County)

Known Required

Utility Name	Adjustment	Type

City of Goodman	No	Sanitary Sewer & Water

Keith Estes

203 W. Barlow St.

Goodman, MO  64843

Phone:  417-364-7316

Email:  wwtp@goodmanmo.net

Rally Networks (Goodman Telephone)	No	Communications

Jim Hernon

816 Oneida Street

Seneca, MO  64865

Phone:  417-776-2244

Email:  jamesh@rallynet.us

Liberty Utilities	Yes	Power

Allec Uber	(see sections 4.1.1, 7.1)

3400 S. Kodiak Road

Joplin, MO  64804

Phone:  417-291-0170

Email:  allec.uber@libertyutilities.com

Local Contact: Duane Myers

Phone:  417-952-0731

Email:  duane.myers@libertyutilities.com

Lumen	No	Communications

Kimberly Singleton, Engineering Manager	(see section 7.2)

Phone:  419-631-4683

Email:  kimberly.singleton@lumen.com

Olsson (Lumen’s contract engineer)

Sandra Munoz-Cabuya

7301 W. 133rd Street, Suite 200

Overland Park, KS  66213

Phone:  913-748-2646

Email:  smunozcabuya@olsson.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

Mediacom	No	Communications

Evan Watson

1110 Breckenridge Rd.

Mt. Vernon, MO  65712

Phone:  417-316-9164

Email:  ewatson@mediacomcc.com

Spire Energy	No	Gas

Baylee Godat	(see section 7.3)

3025 SE Clover Dr.

Lee’s Summit, MO  64082

Phone:  816-334-8075

Email:  baylee.godat@spireenergy.com

Location 8 – MO59 at Bus71 in Anderson (McDonald County)

Known Required

Utility Name	Adjustment	Type

City of Anderson	No	Sanitary Sewer & Water

Ben Shoemaker

103 W. Beaver St.

Anderson, MO  64831

Phone:  417-845-6463

Email:  afd310@yahoo.com

Liberty Utilities	Yes	Power

Allec Uber	(see sections 4.1.1, 8.1)

3400 S. Kodiak Road

Joplin, MO  64804

Phone:  417-291-0170

Email:  allec.uber@libertyutilities.com

Local Contact: Duane Myers

Phone:  417-952-0731

Email:  duane.myers@libertyutilities.com

Liberty Connect	No	Communications

Landon Dobbs

720 Schifferdecker Ave.

Joplin, MO  64802

Phone:  417-483-2460

Email:  landon.dobbs@libertyutilities.com

Lumen	No	Communications

Kimberly Singleton, Engineering Manager	(see section 8.2)

Phone:  419-631-4683

Email:  kimberly.singleton@lumen.com

Olsson (Lumen’s contract engineer)

Sandra Munoz-Cabuya

7301 W. 133rd Street, Suite 200

Overland Park, KS  66213

Phone:  913-748-2646

Email:  smunozcabuya@olsson.com

McDonald County Telephone	No	Communications

Todd Clay

704 Main Street

Pineville, MO  64856

Phone:  417-529-6333

Email:  todd@southwestmo.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

Spire Energy	No	Gas

Baylee Godat

3025 SE Clover Dr.

Lee’s Summit, MO  64082

Phone:  816-334-8075

Email:  baylee.godat@spireenergy.com

Verizon	No	Communications

Bryan Burger

10740 Nall Ave., Suite 400

Overland Park, KS  66211

Phone:  816-204-4494

Email:  bryan.burger@verizon.com

Location 9 – Bus71 at Cedar Road in Anderson (McDonald County)

Known Required

Utility Name	Adjustment	Type

City of Anderson	No	Sanitary Sewer & Water

Ben Shoemaker

103 W. Beaver St.

Anderson, MO  64831

Phone:  417-845-6463

Email:  afd310@yahoo.com

New-Mac Electric Coop.	Yes	Power

Jeremy Harbaugh	(see section 9.1)

12105 E. Highway 86

Neosho, MO  64850

Phone:  417-850-0834

Email:  jharbaugh@newmac.com

Lumen	No	Communications

Kimberly Singleton, Engineering Manager

Phone:  419-631-4683

Email:  kimberly.singleton@lumen.com

Olsson (Lumen’s contract engineer)

Sandra Munoz-Cabuya

7301 W. 133rd Street, Suite 200

Overland Park, KS  66213

Phone:  913-748-2646

Email:  smunozcabuya@olsson.com

McDonald County Telephone	No	Communications

Todd Clay

704 Main Street

Pineville, MO  64856

Phone:  417-529-6333

Email:  todd@southwestmo.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

Mediacom	No	Communications

Evan Watson

1110 Breckenridge Rd.

Mt. Vernon, MO  65712

Phone:  417-316-9164

Email:  ewatson@mediacomcc.com

OzarksGo	No	Communications

Devin Taylor

3641 W. Wedington Dr.

Fayetteville, AR  72704

Phone:  479-287-6793

Email:  dtaylor@ozarksgo.net

Spire Energy	No	Gas

Baylee Godat

3025 SE Clover Dr.

Lee’s Summit, MO  64082

Phone:  816-334-8075

Email:  baylee.godat@spireenergy.com

Location 10 – Bus71 at Route W in Pineville (McDonald County)

Known Required

Utility Name	Adjustment	Type

City of Pineville	No	Sanitary Sewer & Water

Chris Tinsley

503 Main Street

Pineville, MO  64856

Phone:  417-223-4368

Email:  cityofpineville@gmail.com

Liberty Utilities	Yes	Power

Allec Uber	(see sections 4.1.1, 10.1)

3400 S. Kodiak Road

Joplin, MO  64804

Phone:  417-291-0170

Email:  allec.uber@libertyutilities.com

Local Contact: Todd Martin

Phone:  417-291-2801

Email:  james.martin2@libertyutilities.com

Lumen	No	Communications

Kimberly Singleton, Engineering Manager

Phone:  419-631-4683

Email:  kimberly.singleton@lumen.com

Olsson (Lumen’s contract engineer)

Sandra Munoz-Cabuya

7301 W. 133rd Street, Suite 200

Overland Park, KS  66213

Phone:  913-748-2646

Email:  smunozcabuya@olsson.com

McDonald County Telephone	No	Communications

Todd Clay

704 Main Street

Pineville, MO  64856

Phone:  417-529-6333

Email:  todd@southwestmo.com

MoDOT – Signals, Lighting, ITS	Yes	Signals, Lighting, ITS

Shannon Johnson	(see section 1.2)

2800 Stephens Blvd.

Joplin, MO  64804

Phone:  417-291-6195

Email:  shannon.johnson@modot.mo.gov

OzarksGo	No	Communications

Devin Taylor

3641 W. Wedington Dr.

Fayetteville, AR  72704

Phone:  479-287-6793

Email:  dtaylor@ozarksgo.net

Spire Energy	No	Gas

Baylee Godat	(see section 10.2)

3025 SE Clover Dr.

Lee’s Summit, MO  64082

Phone:  816-334-8075

Email:  baylee.godat@spireenergy.com

1.1  Disclaimer and Verification of Utility Information.  The existence and approximate location of utility facilities known to exist, as shown on the plans, are based upon the best information available to the Commission at this time.  This information is provided by the Commission "as-is" and the Commission expressly disclaims any representation or warranty as to the completeness, accuracy, or suitability of the information for any use.  Reliance upon this information is done at the risk and peril of the user, and the Commission shall not be liable for any damages that may arise from any error in the information.  It is, therefore, the responsibility of the contractor to verify the above listing information indicating existence, location and status of any facility.  Such verification includes direct contact with the listed utilities.

1.2  Project Scope.  The entire scope of this project is to upgrade MoDOT’s signal facilities.  The proposed improvements are included within plans and specifications for the project.  The contractor shall install and/or modify the equipment as shown in the plans and job special provisions.  All cost associated with this work shall be completely covered in the contractor’s submitted bid prices for the signal and lighting items included in the roadway contract.  Special details and requirements regarding the new secondary power connections are included in the Utility JSP for each individual intersection.

1.3  Potholing of Utilities.  The Contractor shall field verify that the proposed traffic signal base locations will not need to be shifted to avoid utilities prior to ordering the traffic signal equipment.  The Contractor shall be proactive and pothole all utilities falling within the locate tolerance for the proposed signal bases.  If a conflict is determined, the Contractor shall shift the signal base location, as approved by the Engineer to mitigate the conflict.  The Contractor shall coordinate construction activities with the utilities and take measures to ensure the integrity of the existing facilities are not disturbed during construction.  The contractor will be compensated for the additional mast arm length, if required.  No direct payment will be made for compliance to this specification.

1.4  Overhead Primary Electric.  Various utilities listed above have overhead lines within the project limits in the vicinity of the Contractor’s work.  The contractor shall comply with the Missouri Overhead Powerline Safety Act; this statute makes it illegal for an unauthorized person or entity to work or bring equipment within 10 feet of a high voltage line that has not been covered or de-energized.  The purpose of the Missouri Overhead Powerline Safety Act is to ensure the safety of the public when working around overhead power lines.  If the contractor needs line cover when working near a primary powerline, then the contractor shall notify that utility owner a minimum of 14 days in advance of needing line cover.  Most power providers perform this service free of charge for municipally driven projects.  The contractor shall be responsible for any damage to the overhead lines caused by their operations.  There will be no direct payment for compliance to this specification.

1.5  LP49 at MO52 in Butler.  Utilizing the existing Type 1 Power Supply.  There are no known utility impacts at this location.

2.0  US54 at Park Street in El Dorado Springs.

2.1  Brightspeed.  Brightspeed has copper and fiber facilities attached to the City’s power pole.  If the City must replace the existing pole with a taller structure as indicated in 2.2.1 below, Brightspeed will need to transfer their facilities to the new pole.

2.2  City of El Dorado Springs - Electric.  MoDOT will be obtaining new secondary power from the City of El Doradro Springs.  The power source will come from the three phase pole located in the southwest quadrant of the intersection.  The roadway contractor will be required to supply and install the riser conduit, the conduit and wire from the power pole to the new Type 2 Power Supply ensuring there is enough wire to reach the transformer at the top of the pole.  City crews will make the new secondary connection at the top of the pole and disconnect the secondary to the existing power supply.  The roadway contractor will be responsible for disposing of the existing power supply.  Cost of the riser conduit and wire is to be included in the cost of the Type 2 Power Supply.  Removal of the old power supply is to be included in within the contractor’s LS cost for Removal of Improvements.

2.2.1  Vertical Clearance.  At the time of project advertisement, the City was still evaluating the vertical clearance between the mast are on Post 1 and the overhead three phase primary power.  If the 10ft minimum vertical clearance cannot be obtained, then the City intends to replace the existing pole with a taller structure.  The pole replacement, if necessary, will be done just prior to the contractor’s signal work.  The contractor shall verify with the City that the minimum clearance issue has been resolved.  If pole replacement is necessary, then the contractor shall provide their tentative construction schedule to the City so they can plan accordingly.

2.3  Fidelity.  Fidelity has a CATV line attached to the City’s power pole.  If the City must replace the existing pole with a taller structure as indicated in 2.2.1 above, Fidelity will need to transfer their line to the new pole.

2.4  Sho-Me Technologies.  Sho-Me has a fiber attached to the City’s power pole.  If the City must replace the existing pole with a taller structure as indicated in 2.2.1 above, Sho-Me will need to transfer their fiber to the new pole.

2.5  Spire.  Sprie has an existing gas main running parallel to US54 along the south side of the roadway.  As-built records indicate this main is 40” deep.  The roadway contractor shall verity Spire’s main has been located prior to performing any excavation and exercise caution when installing the new signal equipment in close proximity to this facility.

3.0  US65 at MO32 in Buffalo.  Utilizing the existing Type 2 Power Supply and lighting controller.  There are no known utility impacts at this location.

4.0  MO43 at 41st Street in Joplin.

4.1  Liberty Utilities.  MoDOT will be obtaining new secondary power from Liberty.  The power source will come from a new transformer installed by Liberty on an existing three phase pole generally located at Sta 34+04, 83’LT.  The roadway contractor will be responsible for providing and installing the first riser conduit on the pole (see 4.1.1 below) and the conduit run from the pole going south to the new Type 2 Power Supply located in the NE quadrant of MO43 and 41st St.  In addition to the conduit run, the roadway contractor shall provide and install the wire from the Type 2 Power Supply to Liberty’s pole insuring there is enough wire at the pole to reach the new transformer set by Liberty.  Since the power source supports primary power, Liberty will provide and install the remaining riser conduit up the pole to the transformer and make the connection.  The conduit run between Liberty’s pole and the new Type 2 Power Supply will owned/maintained by Liberty after acceptance.  The contractor is advised that Liberty has sole discretion for required corrections before final acceptance.  Liberty will require a minimum cover of 30” above the new conduit run.  Liberty will also require rigid steel sweeps at the pole and at the power supply with 2” PVC conduit between the sweeps.  The roadway contractor shall contact McGwire Rice (see contact information above) with Liberty a minimum of 5 days in advance of starting the work for the new secondary power.  The contractor is advised that Liberty will require verification of conduit depth before the trench can be backfilled.  Once the new power supply has been energized, Liberty will remove the overhead secondary feed to the existing Type 1 Power Supply located between SB MO43 and west outer road, south of 41st Street.  The roadway contractor will be responsible for removing the old service pole.  Payment for the additional conduit run and wire will be paid at the contract unit price.  Cost of the riser conduit is to be included in the cost of the Type 2 Power Supply.  Removal of the old wood service pole is to be included in the contractor’s LS cost of Removal of Improvements.

4.1.1  Standard Plan for Liberty Riser.  Liberty Standard Plans are not available on their website.  The roadway contractor shall follow the details as outlined in the plan shown below when installing the riser conduit:

4.2  Spire.  Spire has a 4” plastic gas main crossing MO43 near Sta 37+90.  This main is a one-way feed.  As built records indicate the main is 60 inches deep so there is no apparent conflict.  The contractor shall exercise caution when installing the 15” median drainage pipe over the top of Spire’s main.

5.0  LP49 at Waldo Hatler Drive in Neosho.

5.1  AT&T.  AT&T has a high-profile fiber installed within duct running parallel along the south side of Waldo Hatler crossing LP49 near Sta 491+34.  The proposed Type 2 Power Supply will be installed in close proximity to this fiber.  The contractor shall verify the location of this high-profile facility and exercise caution when installing the new power supply.  Any damage to the fiber caused by the contractor’s operations shall be repaired and/or replaced solely at the contractor’s expense.

5.2  Liberty Utilities.  MoDOT will be obtaining new secondary power from Liberty.  The power source will come from an existing pole supporting secondary power generally located at Sta 491+64, 55’RT.  This pole in the SW quadrant has an existing luminaire.  The roadway contractor will be responsible for providing and installing the entire riser conduit on the pole (see 4.1.1 above) and the conduit run from the pole going northeast to the new Type 2 Power Supply.  In addition to the conduit run, the roadway contractor shall provide and install the wire from the Type 2 Power supply to Liberty’s pole insuring there is enough wire at the pole to reach the existing secondary power at the top of the pole.  The conduit run between Liberty’s pole and the new Type 2 Power Supply will owned/maintained by Liberty after acceptance.  The contractor is advised that Liberty has sole discretion for required corrections before final acceptance.  Liberty will require a minimum cover of 30” above the new conduit run.  Liberty will also require rigid steel sweeps at the pole and at the power supply with 2” PVC conduit between the sweeps.  The roadway contractor shall contact Bill Corlett (see contact information above) with Liberty a minimum of 5 days in advance of starting the work for the new secondary power.  The contractor is advised that Liberty will require verification of conduit depth before the trench can be backfilled.  Once the new power supply has been energized, Liberty will remove the overhead secondary feed to the existing Type 1 Power Supply.  The roadway contractor will be responsible for removing the old service pole.  Payment for the riser, conduit, and wire between Liberty’s pole and new power supply is to be included in the cost of the Type 2 Power Supply.  Removal of the old wood service pole is to be included in contractor’s LS cost of Removal of Improvements. Liberty will be responsible for removing the existing luminaire on the drop pole.

5.3  Lumen.  Lumen and Level 3 (legacy fiber) have high-profile fibers installed within duct running parallel along the west side of LP49 crossing Waldo Hatler near Sta 732+25.  Proposed signal base 2 and pullbox 2 in the NW quadrant will be installed in close proximity to these fibers.  The contractor shall verify the location of these high-profile facilities and exercise caution when installing the new signal base and pullbox.  Any damage to the fiber caused by the contractor’s operations shall be repaired and/or replaced solely at the contractor’s expense.

6.0  US60 at Oak Ridge Drive in Neosho.

6.1  Liberty Utilities Secondary.  MoDOT will be obtaining new secondary power from Liberty.  The power source will come from an existing pole generally located at Sta 713+00, 172’RT.  The roadway contractor will be responsible for providing and installing the entire riser conduit on the pole (see 4.1.1 above) and the conduit run from the pole going northwest to the new Type 2 Power Supply located in the SE quadrant of US60 and Oak Ridge Dr.  In addition to the conduit run, the roadway contractor shall provide and install the wire from the Type 2 Power supply to Liberty’s pole insuring there is enough wire at the pole to reach the existing secondary power at the top of the pole.  The conduit run between Liberty’s pole and the new Type 2 Power Supply will owned/maintained by Liberty after acceptance.  The contractor is advised that Liberty has sole discretion for required corrections before final acceptance.  Liberty will require a minimum cover of 30” above the new conduit run.  Liberty will also require rigid steel sweeps at the pole and at the power supply with 2” PVC conduit between the sweeps.  The roadway contractor shall contact Bill Corlett (see contact information above) with Liberty a minimum of 5 days in advance of starting the work for the new secondary power.  The contractor is advised that Liberty will require verification of conduit depth before the trench can be backfilled.  Once the new power supply has been energized, Liberty will remove the overhead secondary feed to the existing Type 1 Power Supply.  The roadway contractor will be responsible for removing the old service pole.  Payment for the additional conduit run and wire will be paid at the contract unit price.  Cost of the riser conduit and wire is to be included in the cost of the Type 2 Power Supply.  Removal of the old wood service pole is to be included in within the contractor’s LS cost for Removal of Improvements.

6.2  Liberty Utilities Lighting Removal.  As part of the roadway improvements, the contractor shall remove the existing steel light poles and foundations in the NW and SE quadrants of the intersection.  These lights have a direct feed from a Liberty transformer located on a pole west of Oak Ridge between the north outer road and mainline US60.  The contractor shall contact Bill Corlett with Liberty a minimum of 5 days in advance of needing these lights disconnected from the transformer.  The contractor shall salvage the existing breakaway base on both light poles and transport those bases to MoDOT’s signal shop located at 2800 Stephens Blvd. in Joplin, MO.  The contractor shall notify Shannon Johnson with MoDOT at (417) 291-6195 a minimum of 48 hours in advance to schedule delivery.  The existing steel light poles, mast arms, and luminaires shall become the property of the contractor and disposed of off-site.  Cost for compliance with this specification shall be included within the contractor’s LS cost for Removal of Improvements.

7.0  MO59 at Route C in Goodman.

7.1  Liberty Utilities.  MoDOT will be obtaining new secondary power from Liberty.  The power source will come from an existing pole supporting secondary power generally located at Sta 87+97, 72’LT.  This pole in the SW quadrant provides the secondary feed to MoDOT’s existing Type 1 Power Supply and to the City of Goodman sign.  The roadway contractor will be responsible for providing and installing the entire riser conduit on the pole (see 4.1.1 above) and the conduit run from the pole going north to the new Type 2 Power Supply.  In addition to the conduit run, the roadway contractor shall provide and install the wire from the Type 2 Power supply to Liberty’s pole insuring there is enough wire at the pole to reach the existing secondary power at the top of the pole.  The conduit run between Liberty’s pole and the new Type 2 Power Supply will owned/maintained by Liberty after acceptance.  The contractor is advised that Liberty has sole discretion for required corrections before final acceptance.  Liberty will require a minimum cover of 30” above the new conduit run.  Liberty will also require rigid steel sweeps at the pole and at the power supply with 2” PVC conduit between the sweeps.  The roadway contractor shall contact Duane Myers (see contact information above) with Liberty a minimum of 5 days in advance of starting the work for the new secondary power.  The contractor is advised that Liberty will require verification of conduit depth before the trench can be backfilled.  Once the new power supply has been energized, Liberty will disconnect the secondary feed to MoDOT’s existing Type 1 Power Supply.  The roadway contractor will be responsible for removing the old power supply from Liberty’s pole.  The existing service pole is to remain in place as it will continue to feed secondary power to Goodman’s sign.  Payment for the riser, conduit, and wire between Liberty’s pole and new power supply is to be included in the cost of the Type 2 Power Supply.  Removal of the old power supply is to be included in contractor’s LS cost of Removal of Improvements.

7.2  Lumen.  Lumen mapping indicates their Level 3 fiber is not shown on the topographic survey.  This fiber runs parallel to MO59 generally located 28ft east of the east edge of pavement.  The roadway contractor shall verify this fiber is located prior to beginning any excavation operations.  It may be necessary to pothole and shift the proposed signal equipment as outline in section 1.3 above to clear the Level 3 cable.

7.3  Spire.  Spire mapping indicates they have facilities within the project limits that are not shown on the topographic survey.  They have a gas main wrapping around the northwest quadrant running parallel with the water main.  This gas is believed to fall on the roadway sides of the water main.  Spire also has a second main running parallel to Route C/Splitlog Ave. along the south side of the roadway.  The main is shown to run southeast of the existing signal equipment in the southeast quadrant.  Neither main is anticipated to be in conflict with the proposed improvements.  The roadway contractor shall verify Spire’s gas mains are located prior to beginning any excavation operations.  It may be necessary to pothole and shift the proposed signal equipment as outline in section 1.3 above to clear Spire’s facilities.

8.0  Bus71 at MO59 in Anderson.

8.1  Liberty Utilities.  MoDOT will be obtaining new secondary power from Liberty.  The power source will come from an existing pole supporting secondary power generally located at Sta 386+38, 81’RT.  This pole in the NW quadrant supports MoDOT’s existing Type 1 Power Supply and the OH feeds to both of Liberty’s streetlight poles.  The roadway contractor will be responsible for providing and installing the entire riser conduit on the pole (see 4.1.1 above) and the conduit run from the pole going southeast to the new Type 2 Power Supply.  In addition to the conduit run, the roadway contractor shall provide and install the wire from the Type 2 Power supply to Liberty’s pole insuring there is enough wire at the pole to reach the existing secondary power at the top of the pole.  The conduit run between Liberty’s pole and the new Type 2 Power Supply will owned/maintained by Liberty after acceptance.  The contractor is advised that Liberty has sole discretion for required corrections before final acceptance.  Liberty will require a minimum cover of 30” above the new conduit run.  Liberty will also require rigid steel sweeps at the pole and at the power supply with 2” PVC conduit between the sweeps.  The roadway contractor shall contact Duane Myers (see contact information above) with Liberty a minimum of 5 days in advance of starting the work for the new secondary power.  The contractor is advised that Liberty will require verification of conduit depth before the trench can be backfilled.  Once the new power supply has been energized, Liberty will disconnect the secondary feed to MoDOT’s existing Type 1 Power Supply.  The roadway contractor will be responsible for removing the old power supply from Liberty’s drop pole.  Payment for the riser, conduit, and wire between Liberty’s pole and new power supply is to be included in the cost of the Type 2 Power Supply.  Removal of the old power supply is to be included in contractor’s LS cost of Removal of Improvements.  Liberty will be responsible for removing the two steel streetlight poles and the OH secondary to both poles.

8.2  Lumen.  Lumen has a handhole located at Sta 386+29, 78’RT.  Mapping shows 2 cables in the same duct going north out of this handhole.  South of this handhole, Lumen is showing 3 separate cables with individual ducts.  The topographical survey is only showing one line south of the handhole.  The roadway contractor shall verify all of Lumen’s fibers are located prior to beginning any excavation operations.  The contractor is advised that MoDOT new secondary power feed will cross the three cables south of Lumen’s handhole.

9.0  Bus71 at Cedar Road in Anderson.

9.1  New-Mac Electric Cooperative.  MoDOT will be obtaining new secondary power from New-Mac.  The power source will come from an existing three phase pole in the northeast quadrant generally located at Sta 73+54, 69’LT.  This three phase pole currently supports MoDOT’s existing Type 1 Power Supply.  The roadway contractor shall furnish a new Type 1 Power Supply with a 120V Lighting Controller for this location.  Since the new power supply will be install on a pole supporting primary power, New-Mac Electric will install the new Type 1 Power Supply on the pole and make the secondary connection at the transformer.  The roadway contractor shall contact Jeremy Harbaugh (see contact information above) with New-Mac a minimum of 5 days in advance of starting the work for the new secondary power.  All conduit and wire downstream of the new power supply and lighting controller will be MoDOT’s responsibility to own and maintain upon acceptance.  The roadway contractor will be responsible for disposing of the old Type 1 Power Supply after New-Mac removes it from the three phase pole.  Payment for the new power supply, conduit, and wire will be made at the contractor’s submitted unit prices for those items.  Disposal  of the old power supply is to be included in contractor’s LS cost of Removal of Improvements.

10.0  Bus71 at Route W in Pineville.

10.1  Liberty Utilities.  MoDOT will be obtaining new secondary power from Liberty.  The power source will come from an existing pole supporting secondary power generally located at Sta 295+01, 84’LT.  This pole in the NE quadrant is the same pole that supports MoDOT’s existing Type 1 Power Supply and the power supply for the light for the US Flag.  The roadway contractor will be responsible for providing and installing the entire riser conduit on the pole (see 4.1.1 above) and the conduit run from the pole going west to the new Type 2 Power Supply.  In addition to the conduit run, the roadway contractor shall provide and install the wire from the Type 2 Power Supply to Liberty’s pole insuring there is enough wire at the pole to reach the existing secondary power at the top of the pole.  The conduit run between Liberty’s pole and the new Type 2 Power Supply will owned/maintained by Liberty after acceptance.  The contractor is advised that Liberty has sole discretion for required corrections before final acceptance.  Liberty will require a minimum cover of 30” above the new conduit run.  Liberty will also require rigid steel sweeps at the pole and at the power supply with 2” PVC conduit between the sweeps.  The roadway contractor shall contact Todd Martin (see contact information above) with Liberty a minimum of 5 days in advance of starting the work for the new secondary power.  The contractor is advised that Liberty will require verification of conduit depth before the trench can be backfilled.  Once the new power supply has been energized, Liberty will disconnect the secondary feed to MoDOT’s existing Type 1 Power Supply.  The roadway contractor will be responsible for removing the old power supply from Liberty’s pole.  Payment for the riser, conduit, and wire between Liberty’s pole and new power supply is to be included in the cost of the Type 2 Power Supply.  Removal of the old power supply is to be included in contractor’s LS cost of Removal of Improvements.  Liberty will be responsible for removing their wood poles with lights as shown in the plans.

10.2  Spire.  Spire mapping indicates they have facilities within the project limits that are not shown on the topographic survey.  They have a gas main wrapping around the sight triangle in the southwest quadrant.  The main is not anticipated to be in conflict with the proposed improvements.  The roadway contractor shall verify Spire’s gas main is located prior to beginning any excavation operations.

# Contractor Quality Control NJSP-15-42

1.0  The contractor shall perform Quality Control (QC) testing in accordance with the specifications and as specified herein.  The contractor shall submit a Quality Control Plan (QC Plan) to the engineer for approval that includes all items listed in Section 2.0, prior to beginning work.

2.0  Quality Control Plan.

- The name and contact information of the person in responsible charge of the QC testing.

- A list of the QC technicians who will perform testing on the project, including the fields in which they are certified to perform testing.

- A proposed independent third party testing firm for dispute resolution, including all contact information.

- A list of Hold Points, when specified by the engineer.

- The MoDOT Standard Inspection and Testing Plan (ITP).  This shall be the version that is posted at the time of bid on the MoDOT website (www.modot.org/quality).

3.0  Quality Control Testing and Reporting.  Testing shall be performed per the test method and frequency specified in the ITP.  All personnel who perform sampling or testing shall be certified in the MoDOT Technician Certification Program for each test that they perform.

3.1  Reporting of Test Results.  All QC test reports shall be submitted as soon as practical, but no later than the day following the test.  Test data shall be immediately provided to the engineer upon request at any time, including prior to the submission of the test report. No payment will be made for the work performed until acceptable QC test results have been received by the engineer and confirmed by QA test results.

3.1.1  Test results shall be reported on electronic forms provided by MoDOT.  Forms and Contractor Reporting Excel2Oracle Reports (CRE2O) can be found on the MoDOT website.  All required forms, reports and material certifications shall be uploaded to a Microsoft SharePoint® site provided by MoDOT, and organized in the file structure established by MoDOT.

3.2  Non-Conformance Reporting.  A Non-Conformance Report (NCR) shall be submitted by the contractor when the contractor proposes to incorporate material into the work that does not meet the testing requirements or for any work that does not comply with the contract terms or specifications.

3.2.1  Non-Conformance Reporting shall be submitted electronically on the Non-Conformance Report form provided on the MoDOT Website.  The NCR shall be uploaded to the MoDOT SharePoint® site and an email notification sent to the engineer.

3.2.2  The contractor shall propose a resolution to the non-conforming material or work.  Acceptance of a resolution by the engineer is required before closure of the non-conformance report.

4.0  Work Planning and Scheduling.

4.1  Two-week Schedule.  Each week, the contractor shall submit to the engineer a schedule that outlines the planned project activities for the following two-week period.  The two-week schedule shall detail all work and traffic control events planned for that period and any Hold Points specified by the engineer.

4.2  Weekly Meeting.  When work is active, the contractor shall hold a weekly project meeting with the engineer to review the planned activities for the following week and to resolve any outstanding issues.  Attendees shall include the engineer, the contractor superintendent or project manager and any foreman leading major activities.  This meeting may be waived when, in the opinion of the engineer, a meeting is not necessary.  Attendees may join the meeting in person, by phone or video conference.

4.3  Pre-Activity Meeting.  A pre-activity meeting is required in advance of the start of each new activity, except when waived by the engineer. The purpose of this meeting is to review construction details of the new activity.  At a minimum, the discussion topics shall include:  safety precautions, QC testing, traffic impacts, and any required Hold Points.  Attendees shall include the engineer, the contractor superintendent and the foreman who will be leading the new activity.  Pre-activity meetings may be held in conjunction with the weekly project meeting.

4.4  Hold Points.  Hold Points are events that require approval by the engineer prior to continuation of work.  Hold Points occur at definable stages of work when, in the opinion of the engineer, a review of the preceding work is necessary before continuation to the next stage.

4.4.1  A list of typical Hold Point events is available on the MoDOT website.  Use of the Hold Point process will only be required for the project-specific list of Hold Points, if any, that the engineer submits to the contractor in advance of the work.  The engineer may make changes to the Hold Point list at any time.

4.4.2  Prior to all Hold Point inspections, the contractor shall verify the work has been completed in accordance with the contract and specifications.  If the engineer identifies any corrective actions needed during a Hold Point inspection, the corrections shall be completed prior to continuing work.  The engineer may require a new Hold Point to be scheduled if the corrections require a follow-up inspection.  Re-scheduling of Hold Points require a minimum 24-hour advance notification from the contractor unless otherwise allowed by the engineer.

5.0  Quality Assurance Testing and Inspection.  MoDOT will perform quality assurance testing and inspection of the work, except as specified herein.  The contractor shall utilize the inspection checklists provided in the ITP as a guide to minimize findings by MoDOT inspection staff.  Submittal of completed checklists is not required, except as specified in 5.1.

5.1  Inspection and testing required in the production of concrete for the project shall be the responsibility of the contractor.  Submittal of the 501 Concrete Plant Checklist is required.

6.0  Basis of Payment.  No direct payment will be made for compliance with this provision.

# No Value Engineering Proposals for 2.5 Inch Perforated Square Steel Tube (PSST) Posts and Concrete Post Anchors for 2.5 Inch Perforated Square Steel Tube (PSST) Posts

1.0  Description.  This project will require 2.5 In. Perforated Square Steel Tube (PSST) Posts and Concrete Post Anchors for 2.5 In. Perforated Square Steel Tube (PSST) Posts as specified in the plans.

2.0  Construction Requirements.  No Contractor initiated Value Engineering Change Proposals (VECPs) or Practical Design Value Engineering Change Proposals (PDVECPs) will be accepted for any part of installing existing signs or new signs on new Perforated Square Steel Tube (PSST) Posts and Concrete Post Anchors different than the 2.5 Inch Perforated Square Steel Tube (PSST) Posts and Concrete Post Anchor for 2.5 Inch Perforated Square Steel Tube (PSST) Posts that is required.

3.0  Method of Measurement.  No measurement will be made.

4.0  Basis of Payment.  No direct payment will be made to comply with this provision.

# Damage to Existing Pavement, Shoulders, Side Roads and Entrances

1.0  Description.  This work shall consist of repairing any damage to existing pavement, shoulders, side roads and entrances caused by contractor operations.  This shall include, but is not limited to, damage caused by the traffic during contractor operations within the project limits including the work zone signing.

2.0  Construction Requirements.  Any cracking, gouging, or other damage to the existing pavement, shoulders, side roads or entrances from general construction shall be repaired within twenty-four (24) hours of the time of damage at the contractor’s expense.  Repair of the damaged pavement, shoulders, side roads, or entrances shall be as determined by the engineer.

3.0  Method of Measurement.  No measurement of damaged pavement or shoulder areas or   side roads or entrances as described above will be made.

4.0  Basis of Payment.  No payment will be made for repairs to existing pavement, shoulders, side roads or entrances damaged by contractor operations.

# Truck Mounted Attenuator (TMA) for Stationary Activities JSP-23-04

1.0  Description.  Provide and maintain Truck Mounted Attenuators (TMA) in accordance with Sec 612 and as specified herein.

2.0  Construction Requirements.  Truck Mounted Attenuators (TMA) shall be used for the work activities indicated in the plans or specified herein.

2.1  Intersection Island and median Construction - any lane closure required for constructing the intersection islands.

2.2  Sidewalk/Crosswalk Construction - any lane closure required for constructing the sidewalk or crosswalk.

2.3  Traffic Signal Equipment Installation - Any lane closure required for installing any traffic signal equipment within the project limits.

2.4  Pavement Marking – any lane closure required for installing pavement marking within the entire project limits.

4.0  Basis of Payment.  Delete Sec 612.5.1 and substitute with the following:

612.5.1  No payment will be made for truck mounted attenuators (TMAs) used in mobile operations or for any TMAs designated as optional.

612.5.1.1  Payment for TMAs required for stationary work activities will be paid for at the contract unit bid price for Item 612-30.01, Truck Mounted Attenuator (TMA), per lump sum.  The lump sum payment includes all work activities that require a TMA, regardless of the number of deployments, relocations, or length of time utilized.  No payment will be made for repair or replacement of damaged TMAs.

# Optional Pavements JSP 06-06H

1.0  Description.  This work shall consist of a pavement composed of either Portland cement concrete or asphaltic concrete constructed on a prepared subgrade.  This work shall be performed in accordance with the standard specifications and as shown on the plans or established by the engineer.

2.0  The quantities shown reflect the total square yards of pavement surface designated for each pavement type as computed and shown on the plans.

2.1  No additional payment will be made for asphaltic concrete mix quantities to construct the required 1:1 slope along the edge of the pavement, or for tack applied between lifts of asphalt.

2.2  No additional payment will be made for aggregate base quantities outside the limits of the final surface area as computed and shown on the plans.  When A2 shoulders are specified, payment for aggregate base will be as shown on the plans.

2.3  The  grading shown on the plans was designed for either pavement option since the thicknesses for HMA and concrete are the same.  For projects with grading in the contract, there will be no adjustment of the earthwork quantities due to adjusting the roadway subgrade for optional pavements.

2.4  The contractor shall comply with Sections 401 through 403 for the asphalt option and Sections 501 and 502 for the concrete option.

2.5  Pavement options composed of Portland cement concrete shall have contrast pavement marking for intermittent markings (skips), dotted lines, and solid intersection lane lines.  The pavement markings shall be in accordance with Section 620.  No additional payment will be made for the contrast pavement markings.

3.0  Method of Measurement.  The quantities of concrete pavement will be measured in accordance with Section 502.14.  The quantities of asphaltic concrete pavement will be measured in accordance with Section 403.22.

4.0  Basis of Payment.  The accepted quantity of the chosen option will be paid for at the contract unit bid price for Item 401-99.05, Optional Pavement, per square yard.

4.1  For projects with previously graded roadbeds, any additional quantities required to bring the roadway subgrade to the proper elevation will be considered completely covered by the pay item for Subgrading and Shouldering.

4.2 Price Adjustment for Fuel. If the contractor accepts the option for fuel adjustment in the bid proposal, a fuel adjustment will be applied in accordance with Sec 109.14 for the type of pavement constructed.

# Pavement Edge Treatment for Drop Off Conditions for Island Removals

1.0 Description.  This work shall consist of providing pavement edge treatment due to construction methods used by the contractor for the island removals.

2.0 Construction Requirements.  The contractor shall perform construction operations so there will be no drop off exceeding 2 inches adjacent to traffic.  The contractor shall install pavement edge treatment at locations where the drop off is greater than 2 inches adjacent to traffic.

3.0  Method of Measurement.  No measurement of pavement edge treatment as described above will be made.  Treatment of any drop off greater than 2 inches shall be considered incidental to and completely covered by other pay items provided in the contract.

4.0  Basis of Payment.  No direct payment will be made to comply with this provision.

# Lump Sum Temporary Traffic Control JSP-22-01B

1.0  Delete Sec 616.11 and insert the following:

616.11 Method of Measurement. Measurement for relocation of post-mounted signs will be made to the nearest square foot of sign area only for the signs designated for payment on the plans. All other sign relocations shall be incidental. Measurement for construction signs will be made to the nearest square foot of sign area. Measurement will be made per each for each of the temporary traffic control items provided in the contract.

616.11.1 Lump Sum Temporary Traffic Control.  No measurement will be made for temporary traffic control items grouped and designated to be paid per lump sum.  The list of lump sum items provided in the plans or contract is considered an approximation and may be subject to change based on field conditions.  This is not a complete list and may exclude quantities for duplicate work zone packages used in simultaneous operations.  The contractor shall provide all traffic control devices required to execute the provided traffic control plans for each applicable operation, stage, or phase.  No measurement will be made for any additional signs or devices needed except for changes in the traffic control plan directed by the engineer.

2.0  Delete Sec 616.12 and insert the following:

616.12 Basis of Payment. All temporary traffic control devices authorized for installation by the engineer will be paid for at the contract unit price for each of the pay items included in the contract. Whether the devices are paid individually, or per lump sum, no direct payment will be made for the following:

(a)  Incidental items necessary to complete the work, unless specifically provided as a pay item in the contract.

(b)  Installing, operating, maintaining, cleaning, repairing, removing, or replacing traffic control devices.

(c)  Covering and uncovering existing signs and other traffic control devices.

(d)  Relocating temporary traffic control devices, including permanent traffic control devices temporarily relocated, unless specifically included as a pay item in the contract.

(e)  Worker apparel.

(f)  Flaggers, AFADs, PFDs, pilot vehicles, and appurtenances at flagging stations.

(g)  Furnishing, installing, operating, maintaining, and removing construction-related vehicle and equipment lighting.

(h)  Construction and removal of temporary equipment crossovers, including restoring pre-existing crossovers.

(i)  Provide and maintaining work zone lighting and work area lighting.

616.12.1 Lump Sum Temporary Traffic Control. Traffic control items grouped together in the contract or plans for lump sum payment shall be paid incrementally per Sec 616.12.1.1. Alternately, upon request from the contractor, the engineer will consider a modified payment schedule that more accurately reflects completion of traffic control work. No payment will be made for any additional signs or devices needed except for changes in the traffic control plan directed by the engineer. Additional items directed by the engineer will be paid for in accordance with Sec 109.4. No adjustment to the price will be made for overruns or underruns of other work or for added work that is completed within existing work zones.

616.12.1.1  Partial payments. For purposes of determining partial payments, the original contract amount will be the total dollar value of all original contract line items less the price for Lump Sum Temporary Traffic Control (LSTTC). If the contract includes multiple projects, this determination will be made for each project. Partial payments will be made as follows:

(a)  The first payment will be made when five percent of the original contract amount is earned. The payment will be 50 percent of the price for LSTTC, or five percent of the original contract amount, whichever is less.

(b)  The second payment will be made when 50 percent of the original contract amount is earned. The payment will be 25 percent of the price for LSTTC, or 2.5 percent of the original contract amount, whichever is less.

(c)  The third payment will be made when 75 percent of the original contract amount is earned. The payment will be 20 percent of the price for LSTTC, or two percent of the original contract amount, whichever is less.

(d)  Payment for the remaining balance due for LSTTC will be made when the contract has been accepted for maintenance or earlier as approved by the engineer.

616.12.1.2  Temporary traffic control will be paid for at the contract lump sum price for Item:

| Item No. | Unit | Description |
| --- | --- | --- |
| 616-99.01 | Lump Sum | Misc. Lump Sum Temporary Traffic Control |

# ADA Compliance and Final Acceptance of Constructed Facilities JSP-10-01C

1.0  Description.  The contractor shall comply with all laws pertaining to the Americans with Disabilities Act (ADA) during construction of pedestrian facilities on public rights of way for this project.  An ADA Checklist is provided herein to be utilized by the contractor for verifying compliance with the ADA law.  The contractor is expected to familiarize himself with the plans involving pedestrian facilities and the ADA Post Construction Checklist prior to performing the work.

2.0  ADA Checklist.  The contractor can locate the ADA Checklist form on the Missouri Department of Transportation website:

www.modot.org/business/contractor_resources/forms.htm

2.1  The ADA Checklist is not to be considered all-inclusive, nor does it supersede any other contract requirements. The ADA checklist is a required guide for the contractor to use during the construction of the pedestrian facilities and a basis for the commission’s acceptance of work.  Prior to work being performed, the contractor shall bring to the engineer’s attention any planned work that is in conflict with the design or with the requirement shown in the checklist.  This notification shall be made in writing. Situations may arise where the checklist may not fully address all requirements needed to construct a facility to the full requirements of current ADA law.  In those situations, the contractor shall propose a solution to the engineer that is compliant with current ADA law using the following hierarchy of resources:  2010 ADA Standards for Accessible Design, Draft Public Rights of Way Accessibility Guidelines (PROWAG) dated November 23, 2005, MoDOT’s Engineering Policy Guidelines (EPG), or a solution approved by the U.S. Access Board.

2.2  It is encouraged that the contractor monitor the completed sections of the newly constructed pedestrian facilities in attempts to minimize negative impacts that his equipment, subcontractors or general public may have on the work.  Completed facilities must comply with the requirements of ADA and the ADA Checklist or have documented reasons for the non-compliant items to remain.

3.0  Coordination of Construction.

3.1  Prior to construction and/or closure on an existing pedestrian path of travel, the contractor shall submit a schedule of work to be constructed, which includes location of work performed, the duration of time the contractor expects to impact the facility and an accessible signed pedestrian detour compliant with MUTCD Section 6D that will be used during each stage of construction.  This plan shall be submitted to the engineer for review and approval at or prior to the pre-construction conference.  Accessible signed detours shall be in place prior to any work being performed that has the effect of closing an existing pedestrian travel way.

3.2  When consultant survey is included in the contract, the contractor shall use their survey crews to verify that the intended design can be constructed to the full requirements as established in the 2010 ADA Standards.  When 2010 ADA Standards do not give sufficient information to construct the contract work, the contractor shall refer to the PROWAG.

3.3  When consultant survey is not included in the contract, the contractor shall coordinate with the engineer, prior to construction, to determine if additional survey will be required to confirm the designs constructability.

4.0  Final Acceptance of Work.  The contractor shall provide the completed ADA Checklist to the engineer at the semi-final inspection.  ADA improvements require final inspection and compliance with the ADA requirements and the ADA Checklist.  Each item listed in the checklist must receive either a “YES” or an “N/A” score.  Any item receiving a “NO” will be deemed non-compliant and shall be corrected at the contractor’s expense unless deemed otherwise by the engineer.    Documentation must be provided about the location of any non-compliant items that are allowed to remain at the end of the construction project.  Specific details of the non-compliant items, the ADA requirement that the work was not able to comply with, and the specific reasons that justify the exception are to be included with the completed ADA Checklist provided to the engineer.

4.1  Slope and grade measurements shall be made using a properly calibrated, 2 foot long, electronic digital level approved by the engineer.

5.0  Basis of Payment.  The contractor will receive full pay of the contract unit cost for all sidewalk, ramp, curb ramp, median, island, approach work, cross walk striping, APS buttons, pedestrian heads, detectible warning systems and temporary traffic control measures that are completed during the current estimate period as approved by the engineer.  Based upon completion of the ADA Checklist, the contractor shall complete any necessary adjustments to items deemed non-compliant as directed by the engineer.

5.1  No direct payment will be made to the contractor to recover the cost of equipment, labor, materials, or time required to fulfill the above provisions, unless specified elsewhere in the contract documents.

# ADA Material Testing Frequency Modifications JSP-23-01

1.0 Description.  This provision revises the Inspection and Testing Plan (ITP) for the construction of ADA compliant features to better match the nature of the work. The Quality Control (QC) testing frequency for the Sections identified below are to be revised as specified.

2.0  Compaction Test on Base Rock Under Sidewalk, Curb Ramps and Paved Approaches.  (Revises ITP Sec 304.3.4) The required test frequency will be one per 600 tons.

3.0  Gradation Test on Base Rock Under Sidewalk, Curb Ramps and Paved Approaches.  (Revises ITP Sec 304.4.1) The required frequency will be one per 500 tons.

4.0  Concrete Plan Checklists.  (Revises ITP Sec 501)  Submittal of the 501 Concrete Plant Checklist will be once per week when the contractor is only pouring curb, sidewalk, paved approaches, and curb ramps.

5.0  Concrete Median, Median Strip, Sidewalk, Curb Ramps, and Curb.  (Revises ITP Sec 608)  The required frequency will be the first truckload for the project and each 100 CUYDs for air and slump thereafter.  Strength will be verified by use of cylinders or maturity meters at a minimum rate of one per 100 CUYD.

6.0 Paved Approaches. (ITP Sec 608)  The required testing of one test from the first truckload per day and each 100 CUYDs for air and slump will remain per ITP.  Strength will be verified by use of cylinders or maturity meters at a minimum rate of one per 100 CUYD.

7.0  Curb Concrete.  (Revises ITP Sec 609)  The required frequency will be the same as Sec 5.0 above.

8.0  Basis of Payment.  No direct payment will be made to the contractor to fulfill the above requirements.

# ADA Compliant Moveable Barricade

1.0  Description.  The work shall consist of providing moveable barricades to satisfy the requirements of the pedestrian traffic control plans as shown in the bidding documents.  The contractor will be responsible for moving the pedestrian barricades to coincide with their planned order of work.

2.0  Construction Requirements.  The contractor shall use a moveable barricade that meets the requirements as established by the ADA.  The pedestrian barricades shall be of self-supporting type having a minimum length of 6 feet per unit.  The face of the barricade shall not extend into adjacent sidewalk considered open for pedestrian use.  The contractor will be responsible for setting and maintaining the pedestrian barricades until all the proposed improvements have been constructed.

3.0  Method of Measurement.  Measurement for ADA Compliant Moveable Barricade will be made per each for each 6 feet (min.) unit provided.

4.0  Basis of Payment.  Payment for all work necessary to fulfill the requirements noted above will be considered completely covered in the contract unit price for Pay Item No. 616-99.02 ADA Compliant Moveable Barricade, per each.  No direct payment will be made for any necessary relocation of the ADA Compliant Moveable Barricade.

# Linear Grading for ADA Facilities - SW

1.0  Description.  This work shall consist of altering the existing roadside features to the required grade and cross sections shown on the plans (if applicable), or to comply with typical sections, running slopes, drop-off and side-slope standards, consistent with the guidelines set forth in the Americans with Disabilities Act (ADA).  This work shall be in accordance with Sections 202 and 207 and accompanying provisions except as modified herein.

2.0  Construction Requirements.  The roadside shall be brought to the required grade and cross section as established in Section 1.0 of this provision, to a uniform appearance, free of sharp breaks or humps. Minor deviations will be allowed, to take advantage of favorable topography, as approved by the engineer.

2.1  The contractor shall remove all existing roadside improvements necessary to facilitate the new sidewalk and curb ramp construction, along with any other roadside removal items at, or adjacent to the pedestrian pathway, as noted in the plans or as approved by the engineer.  This shall include the removal and/or saw cutting at existing raised islands or median strips to construct the pedestrian pathway.  The contractor shall pay special care to existing utility facilities to be used in place or relocated by others.

2.2  The contractor shall be responsible for all excavation and embankment work necessary to facilitate construction of new ADA compliant facilities; normally consisting of subgrade and subsequent finished grading for sidewalks, curbs, curb ramps; and may include miscellaneous grading work for items such as ditches, entrances, paved approaches, driveways and pipes, at or adjacent to proposed new sidewalk facilities.

2.3  By this provision, it may be necessary to excavate, stockpile, and haul some material within the project limits.  Due to staging and/or Right-of-Way constraints, it may be necessary to waste unusable material off Right-of-Way, and/or haul a replacement volume of material back to achieve the desired grades.

2.4  All removals of Portland or Asphaltic Concrete performed under this provision will require saw-cutting a neat/clean edge along the removal lines at no direct pay, unless otherwise provided for in the contract.

3.0  Method of Measurement.  Measurement of Linear Grading for ADA Facilities will be made along the length of the new sidewalk and/or curb ramp installed, along each side of the roadway where sidewalk work is to be performed, and along the centerline length of each driveway, entrance, or paved approach as shown on the plans.  Measurement will be made to the nearest 1-foot for each sidewalk work area, totaled, and paid to the nearest 1-foot for final pay.  Final field measurement will not be required except where appreciable errors are found, or authorized changes have been made.

4.0  Basis of Payment.  The accepted quantities of Linear Grading for ADA Facilities will be paid for at the contract unit price for item 207-99.03, Linear Grading for ADA Facilities, Linear Foot, and will be considered as full compensation for all labor, equipment, material, waste fees, disposal agreements, material acquisition, or other construction costs involved to complete the described work.

4.1  No direct payment will be made for “REMOVAL OF IMPROVEMENTS” associated with the removal and disposal of sidewalks, curbs, curb ramps, entrances, and other incidentals required for construction of the new sidewalk and/or curb ramps.

# Curb Ramps and Sidewalk – SW

1.0  Description. Construction of concrete curbs, aprons, curb ramps, transition areas, sidewalk and landings shall be in accordance with applicable portions of Sections 608 & 609 of the Standard Specification and Standard Plans for Highway Construction 608.10, as shown on the plans, and meet ADA requirements.

- Construction Requirements. This work shall include, but is not limited to, sidewalk construction including landings, joint construction, aggregate base, compaction, apron modifications, transition area, curb ramp construction, Type S Curb or Type A Curb installation (as required), tie bars or dowel bars (as required), clean-up, etc. for each location shown on the plans.

The following requirements shall be applicable to construction of this project:

    - Existing curb, curb and gutter, sidewalk, shoulders, etc. that are adjacent to a designated curb ramp and/or sidewalk improvement area that is damaged during construction shall be replaced/repaired to match existing materials and condition.

    - Variable height curb along the roadside may be constructed monolithic or separate depending on construction operations. Integral curb shall be doweled to the existing gutter or pavement. - Integral or Type S-curb shall be used along the existing right-of-way when constructing curb ramps as shown on the plans. The cost of the curb is included in pay limits of the curb ramp.

    - The transition area shall be 8” thick and tied to the existing roadway pavement and existing paved approach or sidewalk it is matching.

    - Curing compound for all concrete construction shall be a clear or translucent color. The white pigmented option or other colored compound will not be allowed.

    - Adjacent grass areas, landscaping, irrigation systems (lines, sprinkler heads, control boxes), pavement, etc. disturbed by curb ramp or sidewalk construction shall be repaired or replaced to match or exceed existing conditions.

    - Sod quantities are included for adjacent areas. More or less sod may be required depending on actual field conditions.

3.0 Method of Measurement. Curb ramps and concrete sidewalk will be measured to the nearest 1/10 square yard. Measurement of incidental items required to complete all aspects of construction for the above noted items at each new curb ramp and sidewalk location will not be made individually unless specified elsewhere in the contract.

4.0 Basis of Payment. All costs incurred by the contractor by reason of compliance to satisfy the above requirements will be considered incidental to and completely covered by the contract unit price for each of the pay items within the contract.

# Accessible Pedestrian Pushbutton Connectivity

- Description.  Connectivity to all accessible pedestrian pushbuttons shall be required for all signalized pedestrian crosswalks at all intersections as shown in the plans.

2.0	Construction Requirements. In addition to Sec 902, all accessible pedestrian pushbutton systems shall have a Bluetooth interface or other hands-free capability and be password protected.  Programming of the APS buttons shall be accessible through a field service application available on both iOS and Android platforms.

3.0	Equipment requirements.  The accessible pedestrian pushbutton system and its components, in form and functionality, shall meet or exceed the requirements of the following documents and standards:

- 2009 MUTCD, Section 4E.09 – 4E.13

- NEMA 250 – 4X

- NEMA TS1, TS2, TS4, Type 170, Type 2070

4.0	Documentation and Support. The contractor shall provide two (2) copies of the operation and maintenance manuals for each installed system.

5.0	Method of Measurement.  No measurement providing connectivity will be made.

6.0	Basis of Payment.  No direct payment for providing connectivity will be made.  Payment for all work necessary to fulfill the requirements above will be considered completely covered in the contract unit price for Pay Item No. 902-49.21, Accessible Pedestrian Signal, per each.

# Signal Controller

- Description. This work shall consist of providing and installing a new 2070 controller with cabinet at the intersections shown on the plans.

- Material Requirements. The new controllers installed with this project shall consist of ATC eX 2070 controllers with OMNI-eX software as manufactured by McCain, Inc. placed inside a 332 cabinet.

2.1 The contractor shall be responsible for providing and installing all necessary items to make the new signal controllers operational. This includes but is not limited to the 2070 controller, the OMNI-eX software, and the 332 cabinet. The engineer will provide the existing cycle lengths, but the contractor shall ultimately be responsible for programming the timings into the new controllers.

3.0 Method of Measurement. Method of measurement will be made per each controller installed by the contractor and acceptable by the engineer.

4.0  Basis of Payment.  Accepted signal controllers will be paid for at the contract unit price for item 902-99.02, Misc. 2070 Controller, per each.

# Signal Detection Disconnection

1.0  Description.  The contractor shall contact the Traffic Management Center to coordinate a new signal timing at a minimum of two (2) working days prior to the disconnection of the signal’s detection capabilities or prior to the milling of an approach with inductive loop detection.

2.0  Contact Information.

Cole Ketchum, Intermediate Traffic Studies Specialist

Southwest District Traffic Management Center

Telephone Number: 417-829-8061

Cell Number: 417-766-3241

Email  Joseph.Ketchum@modot.mo.gov

3.0  Basis of Payment.  No direct pay will be made to the contractor to recover the cost or time required to fulfill the above provision.

# Contractor Furnished, Contractor Installed Radar Detection System

- Description.  This work shall consist of providing radar detection for all traffic signal installations.  The radar detection shall be in accordance with the standard specifications and installed to provide detection at locations as shown on the plans or as directed by the engineer in accordance with Sec 902.

- Equipment.  Radar equipment must meet or exceed all the following requirements.

  - Equipment must be FCC certified.

  - Equipment must meet all NEMA TS2-2003 specifications for traffic control equipment.

  - Each radar unit must be composed of multiple sensors to establish two-dimensional coverage.

  - Radar Detection must be compatible with SDLC inputs.

- Construction Requirements.  The contractor shall be responsible for providing and installing all necessary items to make the new radar detection system operational with stop bar presence detection and count detection for each lane of travel.  Input BIU 9 shall be used for presence detector inputs according to the following chart.

| Vehicle Detection Assignments |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| PRESENCE DETECTION | BIU | IO | Detector | Call Phase | Mvmt |
|  | BIU 9 | 1 | 1 | 1 | SBL |
|  |  | 2 | 2 | 2 | NBT |
|  |  | 3 | 3 | 3 | EBL |
|  |  | 4 | 4 | 4 | WBT |
|  |  | 5 | 5 | 5 | NBL |
|  |  | 6 | 6 | 6 | SBT |
|  |  | 7 | 7 | 7 | WBL |
|  |  | 8 | 8 | 8 | EBT |
|  |  | 9 | 9 |  |  |
|  |  | 10 | 10 | 2 | NBR* |
|  |  | 11 | 11 |  |  |
|  |  | 12 | 12 | 4 | WBR* |
|  |  | 13 | 13 |  |  |
|  |  | 14 | 14 | 6 | SBR* |
|  |  | 15 | 15 |  |  |
|  |  | 16 | 16 | 8 | EBR* |

*Right turn presence detection only used if the RT lane is signalized

BIU 10 and 11 shall be used for count detector inputs according to the following chart.

| Vehicle Detection Assignments |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| COUNT DETECTION | BIU | IO | Detector | Call Phase | Lane |
|  | BIU 10 | 1 | 17 | 1 | SBL 1 |
|  |  | 2 | 18 | 1 | SBL 2 |
|  |  | 3 | 19 | 1 | SBL 3 |
|  |  | 4 | 20 | 2 | NBT 1 |
|  |  | 5 | 21 | 2 | NBT 2 |
|  |  | 6 | 22 | 2 | NBT 3 |
|  |  | 7 | 23 | 2 | NBT 4 |
|  |  | 8 | 24 | 2 | NBR 1 |
|  |  | 9 | 25 | 3 | EBL 1 |
|  |  | 10 | 26 | 3 | EBL 2 |
|  |  | 11 | 27 | 3 | EBL 3 |
|  |  | 12 | 28 | 4 | WBT 1 |
|  |  | 13 | 29 | 4 | WBT 2 |
|  |  | 14 | 30 | 4 | WBT 3 |
|  |  | 15 | 31 | 4 | WBT 4 |
|  |  | 16 | 32 | 4 | WBR 1 |
|  | BIU11 | 1 | 33 | 5 | NBL 1 |
|  |  | 2 | 34 | 5 | NBL 2 |
|  |  | 3 | 35 | 5 | NBL 3 |
|  |  | 4 | 36 | 6 | SBT 1 |
|  |  | 5 | 37 | 6 | SBT 2 |
|  |  | 6 | 38 | 6 | SBT 3 |
|  |  | 7 | 39 | 6 | SBT 4 |
|  |  | 8 | 40 | 6 | SBR 1 |
|  |  | 9 | 41 | 7 | WBL 1 |
|  |  | 10 | 42 | 7 | WBL 2 |
|  |  | 11 | 43 | 7 | WBL 3 |
|  |  | 12 | 44 | 8 | EBT 1 |
|  |  | 13 | 45 | 8 | EBT 2 |
|  |  | 14 | 46 | 8 | EBT 3 |
|  |  | 15 | 47 | 8 | EBT 4 |
|  |  | 16 | 48 | 8 | EBR 1 |

4.0  Method of Measurement.  Method of measurement will be per intersection, complete in place including all necessary incidental items to complete the work.  An intersection is defined as all legs in each direction including all lanes on each leg of the intersection.

5.0  Basis of Payment.  Payment for the installation of the radar detection system will be completely covered by the contract unit price for Pay Item No. 902-99.02, Contractor Furnished, Contractor Installed Radar Detection System, per each.

# Flashing Yellow Arrow Implementation Details

1.0  Description.  This project includes the implementation of flashing yellow arrow (FYA) signals at various intersections as shown on the plans.

- Construction Requirements.  The contractor shall follow the guidance below when implementing the Flashing Yellow Arrow.

2.1  Output file assignments for FYA compact mode in the 332 signal control cabinet are depicted below.

2.2  Any and all required cabinet modules or components to make the Flashing Yellow Arrow function properly shall be supplied and installed by the contractor.  This includes, but is not limited to, load switches, detector cards and loading resistors.

2.3  The contractor shall notify the Commission’s representative listed below one (1) week prior to the desired implementation to obtain the required controller timing and data changes.

Cole Ketchum, Intermediate Traffic Studies Specialist

Southwest District Traffic Management Center

Telephone Number: 417-829-8061

Cell Number: 417-766-3241

Email  Joseph.Ketchum@modot.mo.gov

2.4  Unused load switch outputs may need to be wired to a loading resistor to satisfy conflict monitor voltage requirements.  A 1500 ohm, 25W resistor shall be used.

2.5  Red “flash color” cabinet programming plugs shall be installed for all new or modified left turn phases.

2.6  The contractor shall follow the appropriate conflict monitor unit manual to properly configure and implement the flashing yellow arrow and ensure the traffic signals/phases are safely monitored.  Conflict monitors on this project shall be Eberle Design, Inc( EDI), Model 2010ECLip.  Website for EDI: https://www.editraffic.com/about-us

- Basis of Payment.  No direct payment will be made to the contractor for all costs incurred with compliance of this provision.  All equipment and labor necessary for the work described will be considered incidental to and completely covered by other pay items provided in the contract.

# Retroreflective Back Plates

1.0  Description. This work shall consist of furnishing and installing new traffic signal retroreflective back plates at the locations shown on the plans and in accordance with Sec 902 and 1092.

2.0  Construction Requirements.  Traffic signal retroreflective back plates shall meet the minimum requirements of Sec 1092 and shall conform to Sec 902.  Retroreflective tape will not be accepted as a substitution for a retroreflective back plate.

3.0  Method of Measurement.  Measurement will be made per each.

4.0 Basis of Payment. Payment for furnishing all labor, equipment, materials, and tools necessary to remove and replace the existing signal black plate with a retroreflective back plate will be completely covered by the contract unit price for:

| Pay Item Number | Type / Description | Unit |
| --- | --- | --- |
| 902-99.02 | Retroreflective Back Plates | Each |

# Remove and Relocate CCTV Camera

1.0  Description.  This work shall consist of removing and relocating the CCTV camera at the intersection of US 54 and Park St in El Dorado Springs, MO.

2.0 Construction Requirements.  The contractor shall remove the existing CCTV equipment from the existing pole and cabinet and store all equipment until it is able to be relocated during the project.

2.1  The contractor shall exercise reasonable care in the handling of the equipment during the removal and relocation.  Should any of the equipment be damaged by the contractor's negligence, it shall be replaced at the contractor's expense.  The contractor may request a field meeting with the engineer at the site to inspect the equipment prior to removal.

3.0  Method of Measurement.  Measurement will be made per each.

4.0  Basis of Payment.  Payment for removing and relocating the CCTV camera assembly including labor, materials, equipment, and new cable will be considered completely covered by the contract unit price, Remove and Relocate CCTV Camera.  No additional compensation will be made.

| Pay Item Number | Type / Description | Unit |
| --- | --- | --- |
| 902-99.02 | Remove and Relocate CCTV Camera | Each |

# Wireless Connection

- Description. This work shall consist of providing and installing a wireless communications Subscriber Unit (SU) at the following intersections:

Route 54 at Park St. – El Dorado Springs

Route 43 at 41st St. - Joplin

BL49 at Waldo Hatler Memorial Dr. - Neosho

Route 60 at Oak Ridge Dr. - Neosho

Route 59 at Route at Route C - Goodman

Route 59 at BUS 71 and Route 76 - Anderson

BUS 71 at Cedar St. - Anderson

BUS 71 at Route W - Pineville

- All new communications equipment shall be compatible with any existing communications network and equipment installed along each corridor. To ensure compatibility of the existing network, new wireless communications equipment shall be made by the same manufacturer and shall operate in the same frequency as the existing equipment unless otherwise approved by MoDOT staff.

2.0 Material Requirements. Wireless Subscriber Unit shall include the outdoor wireless unit and antenna, outdoor rated cabling (per manufacturer requirements), lightning surge protection with earth grounding, and ancillary equipment necessary to provide communications. Subscriber Unit’s are allowed to have an integrated wireless radio and antenna. The installation shall include any necessary modifications to provide power connections and mounting of the unit inside the traffic signal cabinets. The contractor is responsible for communications path work, power level settings, antenna positioning, Radio Frequency Interference (RFI) studies and Electro Magnetic Interference (EMI) resolution so that the contractor delivers a fully functional, operational and secure communication network connection as approvedby MoDOT staff.

3.0 Communications. The contractor shall be responsible for providing and installing all necessary items to provide a stable connection between the existing AU and the new wireless SU and provide connectivity to the existing wireless communication links along Kearney St. and the MoDOT area network. The unit shall be installed on the signal pole such that it provides optimal line of sight between wireless AU and SU units. Appropriate connections to the Signal shall be provided.  The contractor shall communicate with MoDOT staff to determine appropriate set-up of wireless devices.

4.0 Method of Measurement. Measurement will be made per each Wireless connection installed by the contractor as approved by the engineer.

5.0 Basis of Payment. Accepted wireless subscriber units will be paid for at the contract unit price for item 902-99.02, Wireless Subscriber Unit, Each.

# Disposition of Existing Signal, Lighting and Network Equipment

1.0  Description. This work shall consist of the disposition of existing signal, lighting, and network equipment as shown on the plans and delivering it to the specified MoDOT maintenance lot.

- Construction Requirements.  All controllers, cabinets, cabinet equipment, network equipment, DMS equipment, antennas, radios, modems, and other equipment noted in the plans shall be removed by the contractor and delivered to the following location:

Springfield Maintenance Lot

2455 N. Mayfair

Springfield, MO 65803

2.1  The contractor shall notify the Commission’s representative 24 hours prior to each delivery by calling the contact listed below.

Joe Dotson, Urban Traffic Supervisor

Phone: (417) 895-7599 or (417) 733-0664

  - The contractor shall exercise reasonable care in the handling of the equipment during the removal and transportation.  Should any of the equipment be damaged by the contractor's negligence, it shall be replaced at the contractor's expense.  Delivery shall be within 2 working days of removal.  All items returned shall be tagged with the date removed, project number and location/intersection.

2.3  Equipment shown on the plans for removal not listed in section 2.0 above shall become the property of the contractor and removed from the project.

- Basis of Payment.  Payment for removal, handling and transportation of all equipment specified will be considered completely covered by the contract unit price for 202-20.10, Removal of Improvements, per lump sum.

# Removal and Delivery of Existing Signs JSP-12-01C

1.0	Description.  All Commission-owned signs removed from the project shall be disassembled, stored, transported, and disposed of as specified herein. Sign supports, structures and hardware removed from the project shall become the property of the contractor.

2.0  Disassembly and Delivery.

2.1  All Commission-owned signs, (excluding abandoned billboard signs), designated for removal in the plans, or any other signs designated by the Engineer, shall be removed from the sign supports and structures, disassembled, stored, transported, and delivered by the contractor to the recycling center for destruction.

2.2  The contractor shall coordinate and make arrangements with the recycling center for delivery of the signs. Sign panels shall be disassembled and/or cut into sizes as required by the recycling center.

2.3  The contractor shall provide the Engineer with a “Sign Delivery Certification” attesting to completion of delivery of all existing sign material from the project to the recycler. In addition, the contractor shall provide to the Engineer a final “Sign Certification of Destruction” from the recycler that documents the total pounds of scrap sign material received from the project and attests that all such material will not be re-purposed and will be destroyed in a recycling process. The contractor can locate the required certification statements from the Missouri Department of Transportation website:

https://www.modot.org/forms-contractor-use

2.4  Funds received from the disposal of the signs from the recycling center shall be retained by the Contractor.

3.0  Basis of Payment.  All costs associated with removing, disassembling and/or cutting, storing, transporting, and disposing of signs shall be considered as completely covered by the contract unit price for Item No. 202-20.10, “Removal of Improvements”, per lump sum.

# Contractor Furnished Surveying and Staking – SW

In addition to the requirements of Section 627 of the Missouri Standard Specifications for Highway Construction, the following shall apply:

1.0  Description.  The contractor shall be responsible for all layout required on the project.  This responsibility shall include, but not be limited to the following:  Construction signing, transition milling, pavement marking, loop detectors, etc.

1.1  The above list is not all inclusive.  The contractor shall have the primary responsibility for these operations.  The contractor shall provide the Resident Engineer with a staking plan layout for approval prior to the installation of signs.  The RE will provide assistance during this layout provided a request is submitted to the RE or Construction Project Manager 48 hours in advance.  This will ensure that all permanently mounted traffic control devices remain consistent with District policy and avoid re-staking.  If the contractor installs any signs without engineer approval, all costs associated with re-staking and/or relocation will be at the contractor’s expense.

1.2  The intent of this provision is to increase the quality of our work zones and minimize negative impacts to the contractor’s schedule that can result from delays in staking.

1.3  Any adjustments to the plan quantities or line numbers established in the contract shall be approved by the Engineer.

2.0  Basis of Payment.  No direct payment will be made to cover the costs associated with these additional requirements.  All costs will be considered completely covered by the unit bid price submitted for Contractor Furnished Surveying and Staking.

# Seeding and Mulching Requirements JSP-25-03

1.0  Seeding.  Seeding shall be in accordance with Sec. 805 except as otherwise stated herein. Cool season grasses shall be utilized in accordance with Standard Plan 805.00.

1.1  Temporary Seeding.  Temporary seeding shall be in accordance with Sec. 806.50 except as otherwise stated herein.

2.0  Mulching.  Mulching shall be in accordance with Sec. 802 except as otherwise stated herein.

3.0  Method of Measurement.  No measurement will be made for seeding, temporary seeding or mulching.  Seeding and mulching of all disturbed areas, including any additional areas disturbed beyond what is shown on the plans, shall be considered included in the single lump sum item provided.

4.0  Basis of Payment.  All labor, equipment, and materials necessary to complete all seeding, temporary seeding and mulching shall be completely covered under the lump sum price for item 805-99.01, Seeding and Mulching - Cool Season Grasses.

# Removal of License Plate Reader by Others

1.0  Description.  This work shall consist of contacting the Flock Safety representative to inform them to remove the license plate reader attached to the signal pole in the northeast quadrant of MO 43 and 41st Street in Joplin.

2.0  Construction Requirements.  The contractor shall contact the Flock Safety representative listed below at least four (4) weeks in advance of the signal pole removal to advise them of the work that will take place and to allow Flock Safety time to remove the license plate reader.

Katelyn McKinley

Permitting Manager

Flock Safety

Phone: (866) 901-1781 (8 am – 8 pm EST Monday-Friday)

Email: Katelyn.mckinley@focksafety.com

3.0  Method of Measurement. No measurement will be made.

4.0  Basis of Payment. No direct payment will be made for contacting Flock Safety.  All costs associated with this work shall be considered incidental to other pay items provided in the contract.